## Slide 1: SOFTWARE PROJECT MANAGEMENT
20XW83

## Slide 3: Introduction To SPM

## Slide 4: Contents
What is a “Project”?
Project life-cycle
The project as a System
What is “Management”?
Problems with Software Projects
Project Control life Cycle
Who are “Stakeholders”?
Information and Control in Organizations
Case-Study

## Slide 5: What is a Project ?
A specific plan or design
A Planned undertaking
A large undertaking Eg. A Public works scheme

## Slide 6: What is a “Project” ?
The following key characteristics that distinguish projects are:
    Planning is required
    Non-routine tasks are involved
    Specific objectives have to be met
    Project has a predetermined time span
    Work is carried out for someone other than yourself
    Work is carried out in several phases
    The resources needs to be constrained
    The work involves several specialisms

## Slide 7: Prioritize the following projects
Producing an edition of newspaper
Putting a robot vehicle on Mars to search for signs of life
Getting Married
Amending a financial system to deal with a common European currency;
A research project into what makes a good HCI
An investigation into the reason why a user has a problem with a computer system
A second year programming lab assignment for a computer science student
Writing an operating system for a new computer
Installing MS-WORD in an organization
LOGIN – 2024 (Technical Symposium)

## Slide 8
20PW01 ABISHEK A

## Slide 9: Project Life-Cycle
Requirements
Analysis
Specification
Design
Coding
Verification &
Validation
Implementation
Maintenance &
Support
Finding out in detail what the users require of the system
Detailed Documentation of what the proposed system is to do
A design that meets the specification has to be drawn up either external or user design
This refers to the language that is used
Testing needs to be done to check the proposed system meets the requirements
Installation of the system after the software has been developed

## Slide 10: Software Projects VS Other Projects
Many of the techniques followed in general project management is also applicable to software projects management.
Invisibility:
Unlike projects related to roads and bridges software projects are not immediately visible.
Complexity:
Per dollar ,pound spent ,software products contains more complexity.
Flexibility:
The ease at which the software's can be changed is usually seen as one of its strength. The software will change based on the environment it is put into.
Conformity : Developers have to conform user requirements.
Physical materials like Iron, steel, cement, governed by physical laws

## Slide 11: The Project as a System
A project is concerned with creating a new system and/or transforming an old one and is a system
System:
The simple definition of the term system is a ‘ set of interrelated parts’.
Subsystems:
The system will itself comprise of subsystems. The are smaller parts of the larger system.
Environment:
Outside the system there will the system’s environment
Open systems:
Open Systems are those that interact with the environment completely.

## Slide 12
20PW02 AKASH A

## Slide 13: What is “Management”?
The open University suggest that management involves the following activities:
Planning - Deciding what is to be done
Organizing - Making arrangements
Staffing - Selecting right people for the job
Directing - Giving instructions
Monitoring - Checking on progress
Controlling - Taking actions to remedy hold-ups
Innovating - Coming up with new solutions
Representing - Liaising with users.

## Slide 14
Paul Duggan is the project manager of a software development company. On Tuesday at 10am he and his fellow section heads have a meeting with their senior manager about the staffing requirements for the coming year. This is based on the work planned for his project for the next year. At 2pm, Paul has a meeting with a senior staff about an important project his section is undertaking. One of the programming staff has just had a road accident and will be hospitalised for some time. It is decided that the project can be kept on schedule by transferring another team member to his project. But this temporary arrangement, may take a week for transferring the staff. Paul has to phone to the Personnel manager about getting a replacement and the user for whom the project work is being done. Identify which of the 8 management responsibilities, Paul was responding to at different points during his day.

## Slide 15
20PW03 AKSHAYA J

## Slide 16: Problems with Software Projects
Problems as per Project Managers
The most commonly experienced problems
Poor estimates and plans
Lack of quality standards and measures
Lack of guidance about making organizational decisions
Lack of techniques to make progress visible
Poor role definition - who does what?
Incorrect success criteria
Problems of a Team member
Inadequate specification of work
Management ignorance of IT
Lack of knowledge of application area
Lack of standards
Lack of up-to-date documentation

## Slide 17: Problems with Software Projects
Lack of training
Deadline pressure
Lack of quality control
Narrow scope technical expertise
Lack communication leading to duplicate of work
Lack of communication between users and technicians
Changing software environments
Preceding activities not completed in time – including the late delivery of products

## Slide 18: PROBLEMS FACED BY CUSTOMERS
SUPPLIER NOT DELIVERING PACKAGE IN TIME
OVER BUDGET
DELAYED BY A YEAR
LACK OF CONFIDENCE
POOR MANAGEMENT
FAILED PROJECT

## Slide 19
20PW04 ANIRUDH BALAKRISHNAN

## Slide 20: Project Control life cycle
Real World
Data
Information
Decisions
Actions
Data
Collection
Data
Processing
Making decisions/
plans
Implementation
Modelling
Define
Objectives

## Slide 21: STAKE HOLDERS
These are who have stake or interest in the project. They might be internal to the project team ,external but within the same organization ,or totally external to the organization
Internal to the project Team:
They will under the direct managerial control of the project leader.
External to the project but within the same organization:
The project leader might need assistance to carry out system testing etc.

## Slide 22: STAKE HOLDER ...
External to both the project team and organization:
External stakeholders might be customers who will benefit from the system that the project implements or contractors who will carry out the work.
‘Theory W’:
Proposed by Boehm and Ross suggests that the manager needs to concentrate on creating situations where all parties involved in the project benefit from it and therefore have an interest in its success.

## Slide 23
Information and Control in Organizations
Hierarchical information and control systems:
With small projects , the project leaders work very closely with the team members and might be carrying out non managerial activities.
Larger projects are likely to have hierarchical management as shown in the fig below
Control
Information

## Slide 24
Levels of decision making and information
Decisions can be grouped into three levels
Strategic decision:
This is essential about deciding objectives. These decisions need to be taken whenever the objectives for the projects are been decided. (Top Management)
Eg. Here afterwards Testing group will be an independent and not a part of the project team
Tactical decision:
This is needed to ensure that the objectives will be fulfilled. The need to formulate a plan of action to meet those objectives. (PM or PL). Eg. Peer review will be done once in 2 days-- Decided by a Project Manager

## Slide 25: Levels of decision making and information…
Operational decision:
This relates to day-to-day work of implementing the project. For e.g. deciding the content of the acceptance tests might come under this. (Team Leader / Team Member)

## Slide 26
Measurement
Software measurements can be divided as,
Performance measures:
These measures the characteristics of the system that been delivered. Eg. Reliability, Efficiency, Usability
Predictive measures:
Predictive measures are taken during development and indicate the performance of the final system likely to be.
Ex. 1. Errors found per KLOC may help to predict the reliability and correctness of a final system.
2. Keystrokes required to carry out a particular transaction may help to predict the time taken by an operator to complete a transaction

## Slide 27
Suggest objectives for the following types of staff : a) Programmer b) Software Project Manager c) Software Sales person d) Systems Analyst In each case suggest two measures of efficiency or effectiveness

## Slide 28: Overview of Project Management
20PW05 BRITNE BINU B M

## Slide 29: Introduction
AIM – To provide a framework of basic steps in Project Planning and control.
Outline of various activities involved in each step of Project Planning.

## Slide 30
An overview of Step Wise

## Slide 31: Steps in Project Planning
Step 0: Select project
Step 1: Identify project scope and objectives
Step 2: Identify project infrastructure
Step 3: Analyze project characteristics
Step 4: Identify project product and activities
Step 5: Estimate effort for each activity

## Slide 32: Steps in Project Planning
Step 6: Identify activity risks
Step 7: Allocate resources
Step 8: Review/publicize plan
Step 9: Execute plan
Step 10: Lower levels of planning

## Slide 33
20PW06 CHANDRASEHAR R

## Slide 34: Step 0: Select project
Step outside the main project planning process
Projects are not initiated out of thin air!!
Some activity has to take place before deciding that the project is worth undertaking.

## Slide 35: Step 1: Identify project scope and objectives
1.1 Identify objectives and measures of effectiveness in meeting them
  Need for agreed objectives of a project
  Success lies in achieving the objectives
1.2 Establish a project authority
  Single overall project authority
  Unity of purpose among those concerned

## Slide 36: Cont..
1.3 Identify all stakeholders in the project and their interests
  Who are the stakeholders?
  All parties who have an interest in the project
1.4 Modify objectives in the light of stakeholder analysis
  Aim is to gain full cooperation of stakeholders
  Modify objectives to achieve cooperation
  Danger of increase in system size..Original objectives may be obscured.
1.5 Establish methods of communications with all parties
  Internal staff – straightforward
  External parties – email etc. can be used

## Slide 37: Step 2: Identify project infrastructure
2.1 Identify relationship between the project and strategic planning
  Identify projects and order of carrying them out
  Establish framework to fit the new system
  Ex: Hardware and Software standards
  Strategic decisions should be documented
2.2 Identify installation standards and procedures
  Change control & configuration management standards
  Quality standards & procedure manual
  A measurement programme to find project status
  P.M should control project activities
  Eg. Time sheets for work done by team members

## Slide 38: Cont..
2.3 Identify Project team organization
  By the Project leader
  High level managerial decisions are taken
  Project Manager should have control over project team
  Example of High level Managerial decision
  Testing group should be independent
  Programmers and system analysts will be in different
  groups

## Slide 39
20PW08 DEEPTHI R

## Slide 40: Step 3: Analyze project characteristics
3.1 Distinguish project as Objective or Product driven
3.2 Analyze other Project characteristics
  Quality based ones
  Ex: Safety critical systems are identified
  Whether it is an IS or process control system ?
  Is it a safety critical system ? Could human life be threatened by a malfunction ?
3.3 Identify high level project risks which will affect the successful outcome of the project

## Slide 41: Cont..
3.4 Take into account User requirements concerning implementation
  Clients will have procedural requirements
  Ex: Govt. departments use SSADM
3.5 Select general lifecycle approach
3.6 Review overall resource estimates
Once the major risks are identified, we have to re-estimate the effort and other resources required to implement the project

## Slide 42: Step 4: Identify project product and activities
More detailed planning of individual activities that will be needed currently is done at this stage
4.1 Identify or describe project products
(deliverables)
  Technical, quality, management products
  Training materials, operating instructions
  Products form a hierarchy
  Relationships should be documented – Product Breakdown Structure (PBS)
4.2 Document generic product flows
  Some products will need some other product to exist first before they can be created. Eg. A program design must be created before the program can be written and program specification must exist before the design can be commences

## Slide 43: PBS-Product Breakdown Structure
Selection Products
Volume Figures
Office Layouts
User Requirements
Invitation to tenders
List of suppliers
User’s modified requirements
Test examples
Existing system description

## Slide 44: Cont..
4.3 Recognize product instances
  Same generic PFD (Product Flow Diagram) relates to more than one instance of a particular type of product
  Each instance to be identified
4.4 Produce ideal Activity network
  Tasks to be carried out are shown
  Order in which they are to be carried out

## Slide 45: An activity network for Accounts-maintenance project

## Slide 46: Cont..
4.5 Modify the ideal to take into account need for stages and checkpoints
  Divide project into stages
  Introduce checkpoint activities
  Sequencing activities will minimize the elapsed time for the project (overall duration)
  It assumes that activity will start soon as, preceding activity is completed

## Slide 47
20PW09 DHIVYA DHARSHNI S V

## Slide 48: Step 5: Estimate effort for each activity
5.1 Carry bottom-up estimates
  Staff effort and other resources required
  Individual activity estimates are calculated
  Summed up to get overall bottom-up estimate
5.2 Revise plan to create controllable activities
  Long activities make a project difficult to control
  Break down into a series of smaller sub-tasks

## Slide 49: Step 6: Identify activity risks
6.1 Identify & quantify activity-based risks
  Seriousness of a risk and likelihood of it occurring
6.2 Plan risk reduction & contingency measures where appropriate
  Avoid or at least reduce some of the identified risks
  Contingency plans – action to be taken if risk materializes
6.3 Adjust overall plans & estimates to take account of risks
By adding new activities, we may reduce risks
For example, training should be given in case of a new technology or language is to be incorporated in the project

## Slide 50: Step 7: Allocate resources
7.1 Identify & allocate resources
  Type of staff needed for each activity
7.2 Revise plans & estimates to take into account resource constraints
  Priority of tasks is established
  Resources are allocated to the tasks based on availability & task priority
  Some team members may be needed for more than one task at a time and in this case an order of priority is established.
  Some tasks may be delayed, while waiting for a team member to become free, which will affect overall project duration

## Slide 51: Step 8: Review/Publicize Plan
8.1 Review quality aspects of the project plan
Before every activity is completed, quality checks have to be passed, so that next activity will be successful if they are dependant on each other.
8.2 Document plans and obtain agreement
  Plans should be carefully documented
  All parties should agree to commitments required of them in the plan

## Slide 52: Step 9 & 10: Execute Plan & Lower levels of planning
Plans will be drawn up in greater detail for each activity
More information will be available near the start of a stage – delaying the detailed planning of later stages

## Slide 53: Software Project Management Chapter 3 : Project Evaluation
20PW10 DHIVYA LAKSHMI S

## Slide 54: 3.1 Introduction
Project evaluation is normally carried out in step 0 of step wise planning of the project.
A Project evaluation will be normally undertaken as part of the feasibility study for any software development.
It will be based on strategic, technical and economic criteria.
3.2 Strategic assessment
Consists of Programme management and Portfolio management.

## Slide 55
Individual projects are seen as a component of programme and should be evaluated and managed as such.
A programme, here, is a collection of projects that all contribute to the same overall organizational goals.
Effective programme management requires that there is a well defined programme goal.
An organization’s projects are selected and tuned to contribute to this goal.
A project must be evaluated according to how it contributes to this programme goal and its viability timing, resourcing and final worth can be affected by the programme as a whole.
3.2.1 Programme management

## Slide 56: 3.2.2 Portfolio management
An organization needs a strategic and operational assessment of a project before taking up it.
These assessment are done by the customer or by the software organization on behalf of the customer.
The project will form part of a portfolio of ongoing and planned projects
The selection of projects must take account of the possible effects on other projects in the portfolio (eg, competition for resources) and the overall portfolio profile (eg, specialization vs diversification).

## Slide 57: 3.3 Technical assessment
Consists of evaluating the required functionality of a project against the hardware and software available.
All the technical parameters of a project are assessed before taking up it.

## Slide 58
20PW11 HEMA VARSHIKA V

## Slide 59: 3.4 Cost-benefit analysis
Done by comparing the expected costs of development and operation
of the system with the benefits of having it in place.
The main condition is that the estimated income and benefits should exceed the estimated costs.
A best suitable project has to be chosen from available options.
Consists of two steps :
  Identifying and estimating all the costs and the benefits of a project –includes estimated development, operational costs and expected benefits.
  Expressing the costs and benefits in common units – net profit has to be calculated by deducting the costs from the total benefit. For this the costs and the benefits have to be expressed in some common monetary units.

## Slide 60: 3.4 Cost
  Costs are easy to identify and quantify in terms of monetary units.
  Development costs – costs involved in the development phase of a project (eg, salaries to the employees
  purchase of s/w & h/w)
  Setup costs – costs of putting the system into place (eg, costs of any new hardware needed to setup the software
  It will also include costs of file conversion, recruitment &
  staff training, purchase of stationery, disks, furniture for
  computers).
  Operational costs – costs of operating the system once it has been installed. (power consumption, etc)

## Slide 61: Benefits
  Benefits are difficult to quantify in monetary terms.
  Direct benefits – these accrue directly from the operation of the proposed system.
  (eg. Salary to clerical staff is reduced due to reduction
  of man power bcos of computerisation)
  Assessable indirect benefits – secondary, indirect benefits.(eg. decrease in number of customer complaints)
  Intangible benefits – long term benefits. Difficult to quantify these. (eg. public approval of the organization in the location where it is based)

## Slide 62: 3.5 Cash flow forecasting
Expenditures like staff wages occur during the development stages of a project.
Such expenditures cannot be deferred until income is received.
Generally in a project expenditures come first, and then the income comes at a later stage.
So we can make a cash flow forecasts.
Its impossible to make cash flow forecasts accurate as it is done at the very initial stage.
Generally in cash flow forecasts inflation are ignored as it increases the uncertainty of the forecasts.
A graph is drawn for the cash flow forecasts which depicts the duration for which the income and expenditure are occuring.

## Slide 63
20PW12 JEEVICKHA K A
20PW13 JERSHA HEARTLY X

## Slide 64: 3.6 Cost-benefit evaluation techniques
A Project is considered only if its benefits outweigh the costs.
The timing of the costs and benefits, benefits relative to the size of the investment are main factors in choosing a project.
Common cost based project evaluation methods:
  Net profit
  Payback period
  Return on investment
  Net present value
  Internal rate of return
  they are explained with the help of a table.

## Slide 65
Year | Project1 | Project2 | Project3 | Project4
0 | -100,000 | -1,000,000 | -100,000 | -120,000
1 | 10,000 | 200,000 | 30,000 | 30,000
2 | 10,000 | 200,000 | 30,000 | 30,000
3 | 10,000 | 200,000 | 30,000 | 30,000
4 | 20,000 | 200,000 | 30,000 | 30,000
5 | 100,000 | 300,000 | 30,000 | 75,000
Net profit | 50,000 | 100,000 | 50,000 | 75,000
Table 3.1 Four Cash Flow Projections – figures are end of year totals
Cash Flow Projections

## Slide 66: 3.6.1 Net profit
Formula : Net Profit = total costs – total income over the life of the project
Advantage : Simple method
Disadvantage : Takes no account of timing of the cash flows
Evaluation (with respect to the Table 3.1): Going by this method, “Project 2“ is chosen. (Highest Net profit ) BUT,
(i) return is relatively low but huge investment (Rs.10Lakhs)
(ii) Project 1 and 3 yield same net profit, but 3 is preferable, as it yields a steady cash inflow, where in 1 much of the income comes at a later stage. In
(iii) If we invest 3,20,000 (for other 3 projects) we get a profit
of Rs.1,75,000.

## Slide 67: 3.6.1 Payback period
Definition : The Payback period is the time taken to break even or pay back the initial investment. Normally, the project with shortest payback period will be chosen as the organization will wish to avoid loan repayments, etc.
Payback periods for each project will occur during the year indicated.
Project 1 - Year 5
Project 2 - Year 5
Project 3 - Year 4
Project 4 = Year 4 (end)
So, we prefer project 3 or 4 than other two projects. But project 3 has shorter payback period than project 4.

## Slide 68: 3.6.1 Payback period
Advantage : Simple, insensitive to small forecasting errors.
Disadvantage : Ignores the overall profitability of the project – doesn’t take into consideration any income/expenditure once the project has broken even.
Evaluation: Project 3 is chosen as it has got the least payback period. BUT, Project 4 has a greater overall profitability and its return is relatively higher than project 3.

## Slide 69: 3.6.3 Return On Investment (ROI)
Also known as the accounting rate of return (ARR).
Formula: ROI = (Average annual profit / Total investment) * 100
where Average annual profit = Total profit / no. of years
Advantage: simple, helps to compare the net profitability to the investment required.
Disadvantage:
Takes no account of the timing of the cash flows.
It tempts to compare the ROI with the current interest rates offered by the bank, but there’s no relation between them (hence misleading).
Evaluation: By this method project 4 (ROI = 12.5%) is chosen. Project 1 and 3 have the same ROIs (10.%), but in project 3, there’s a regular cash inflow, hence it scores over the other.

## Slide 70: 3.6.4 Net Present Value (NPV)
It gives an idea of the estimated worth of a project in terms of current monetary value.
This is done so by discounting future cash flows by a percentage known as the “discount rate”.
Discount Rate - The annual rate by which we discount future earnings.

## Slide 71: NPV PROBLEM
Eg: $100 today is worth more than $100 after a year. $100 today may be worth $91 only after a year, or $91 today is worth $100 after a year. There’s an approx discount of 10% in the value of $100 after a year. This percentage is known as the discount rate.
Formula : Present Value (PV)= value in year t / (1 + r)^t, where ‘r’ is the discount rate, or,
PV = Cash flow of a year * chosen discount factor.
NPV = Sum of all PVs.
Advantage : Takes into account the profitability of a project and the timing of the cash flows.
Disadvantage : Difficulty in deciding the appropriate discount rate.

## Slide 74: NPV contd…
Evaluation 1:
NPV for project 2 is -179,770 (Not worth)
NPV for project 3 is 13,721
NPV for project 4 is 21,662 (Worth)
Project 4 provides greatest NPV and Project 2 is not worth
Evaluation 2: (comparing project 1 and 3) project 3 is chosen, even though both 1 and 3 have the same net profit ($50000), in 1 much of the income comes only at the later stage and its NPV is just $618 as opposed to $13721 of project 3, which is attributed to regular cash inflow and comparatively more income at the initial years itself. Income at the later years gives a little NPV (worth less) than income at the initial years as the value of money tends to decrease with time.

## Slide 75: 3.6.5 Internal Rate of Return (IRR)
The IRR attempts to provide a profitability measure as a percentage return that is directly comparable with interest rates.
Calculated as a “discount rate” that gives “zero NPV”
Project with a greater IRR is chosen.
Advantage: One single method that gives an IRR value which can be directly compared to bank interest rates.
Disadvantage: Does not indicate the absolute size of the return of the project.

## Slide 76: IRR Contd..
Evaluation: (comparing project 1 and 3) project 1 has 10.17% (10% approx) as IRR, and 3 has a little above 15%. Thus investing $100,000 in project 1 having 10% IRR is like earning an interest every year for 10% rate when the amount is invested in bank. For project 3 the interest rate is 3%. Obviously project 3 is chosen because it has got a greater IRR over 1.
(NOTE: IRR can be compared with bank interest rates).

## Slide 79: TUTORIAL
Year | Project A | Project B | Project C
0 | -8,000 | -8,000 | -10,000
1 | 4,000 | 1,000 | 2,000
2 | 4,000 | 2,000 | 2,000
3 | 2,000 | 4,000 | 6,000
4 | 1,000 | 3,000 | 2,000
5 | 500 | 9,000 | 2,000
6 | 500 | -6,000 | 2,000
Net profit | 4,000 | 5,000 | 6,000

## Slide 80
20PW14 KARTHICKPRANAV S N

## Slide 81: 3.7 Risk evaluation
Every project has got an element of risk of some form.
When assessing about a project, the risk involved in it has to be importantly analyzed.
The various risk evaluation techniques are :
  Risk identification and ranking
  Risk and net present value
  Cost-benefit analysis
  Risk profile analysis
  Using decision trees

## Slide 82: 3.7.1 Risk identification and ranking
Identifies risks involved and quantifies it.
Done by constructing a “project risk matrix” using all the possible risks involved in the projects, their importance and their likelihood.
Risks are classified and their importance and likelihood need to be assessed separately.
The list of risks in the project risk matrix should be the same for each project.
Risk | Importance | Likelihood
Software never completed or delivered | High | Unlikely
Response time targets not met | Low | High
Table 3.2 Project Risk Matrix

## Slide 83
Risk | Importance | Likelihood
Software never completed or delivered |  | 
Response time targets not met |  | 
Project cancelled after design stage |  | 
Software Delivered late |  | 
Development budget exceeded <= 20% |  | 
Development budget exceeded > 20% |  | 
Maintenance cost higher than estimated |  | 

## Slide 84: Risk Matrix for a typical software project
Risk | Importance | Likelihood
Software never completed or delivered | High | Unlikely to happen
Response time targets not met | Low | High
Project cancelled after design stage | High | Unlikely to happen
Software Delivered late | Low | Medium
Development budget exceeded <= 20% | Low | Medium
Development budget exceeded > 20% | Medium | Low
Maintenance cost higher than estimated | Low | Low

## Slide 85: 3.7.2 Risk and NPV
When a project is relatively more risky, use a high discount rate to calculate NPV, (even then the NPV is still higher, the project can be considered).
The high discount rate accounts for the “Risk Premium” also.
By a scoring method, we assess a project to be risky of different grade.
For a relatively low risk the risk premium is a less value, and for a high risk one, the risk premium may be more (say 2% for low risk, and 5% for high risk).

## Slide 86: 3.7.3 Cost-benefit analysis
An approach, in which each possible outcome of the risk, its probability, and the corresponding value of the outcome are calculated.
Rather than a single cash flow forecast for a project, a set of cash flow forecasts and their probability of occurrence is considered.
Advantage: helps to evaluate the large projects, where every parameters are uncertain.
Disadvantage: Probability of each outcome has to be correctly decided.

## Slide 87
ABC Corp., a software house is considering developing a payroll application for use in academic institutions and is currently engaged in a cost-benefit analysis. Study of the market has shown that, if they can target it efficiently and no competing products become available, they obtain a high level of sales generating an annual income of $8,00,000. They estimate that there is a 1 in 10 chance of this happening. However, a competitor might launch a competing application before their own launch date and then sales might generate only $1,00,000 per year. They estimate that there is a 30% chance of this happening. The most likely outcome, they believe, is somewhere in between these two extremes – they will gain a market lead by launching before any competing product becomes available and achieve an annual income of $6,50,000. Calculate their expected sales income .

## Slide 88: Cost-benefit analysis contd…
Example:
Sales | Annual Sales Income ($) i | Probability p | Expected Value ($) (i x p)
High | 800, 000 | 0.1 | 80,000
Medium | 650,000 | 0.6 | 390,000
Low | 100,000 | 0.3 | 30,000
Expected Income |  |  | 500,000
ABC Corp’s income forecasts
The above table shows the ABC Corp’s various income forecasts and the expected net income. Decision can be made whether to take upon the project depending upon the expected net income.

## Slide 89: 3.7.4 Risk Profile Analysis
This methods involves varying each of the parameters that affect the project’s cost or benefits to ascertain how sensitive the project’s profitability is to each factor.
A “Risk analysis profile (standard deviation curve)” is constructed using the sensitiveness of the project to a factor.
The original estimates of a project can be varied + or – 5% or so and the benefits can be recalculated to know how critical is that parameter’s estimate that by varying it, to what extent the project’s prospects are affected.
Advantage : Helps to identify the critical parameters for a project.
Disadvantage : More than one parameter cannot be assessed simultaneously.

## Slide 90
20PW15 KARTHIK K M

## Slide 91: 3.7.5 Using decision trees
Used to evaluate whether a risk is important, and if it is, to indicate a suitable course of action.
Used to analyze how a risk will affect future profitability of the project.
This method accounts for the “lost revenue”.
Lost revenue – revenue that was lost because of not releasing a product meeting the consumer requirements.
This method involves constructing a decision tree, which shows the organization to take the correct path of action.

## Slide 92: Eg (Scenario):
ABC Corp wants to extend their software for invoice system.
The consumer for such a software tool is the equipment maintenance business.
They can either extend (CASE 1) the functionalities (features) of the tool or replace (CASE 2) the entire tool.
CASE 1: By this, the tool will generate an NPV of $75000, BUT, if the market expands (many such kind of business comes up), there would be a lost revenue of $100,000 (because the extended tool may not be suitable to latest market scenario, which the replaced system could have met).
CASE 2: By this, the tool generates an NPV of $250000 if the market expands, BUT, if the market doesn’t expand there will be a loss of NPV $50000.

## Slide 93: Using decision trees contd…
The company estimate the likelihood of the market increasing significantly at 20%. Therefore the probability that it will not increase as 80%.
The expected value of extending the system is therefore $40,000 (75,000 * 0.8 – 100,000 * 0.2) and that of
replacing the system is $10,000 (2,50,000 * 0.2 – 50,000 * 0.8).
Hence the ABC Corp decides to go with the option of extending the existing system.
This can be illustrated using a decision tree given below.

## Slide 94
D
Extend
Replace
Expansion 0.2
No Expansion 0.8
Expansion 0.2
No Expansion 0.8
-100,000
75,000
250,000
-50,000
D – Decision point (root of the decision tree)
-ve value for loss
DECISION TREES

## Slide 96: 3.8 Summary
Projects must be evaluated on the strategic, technical and economic grounds.
Economic assessment involves the identification of all costs and income over the lifetime of the system, including its development and operation and checking that the total value of benefits exceeds total expenditure.
Money received in the future is worth less than the same amount of money in hand now, which may be invested to earn interest.

## Slide 97: Summary Contd..
The uncertainty surrounding estimates of future returns lowers their real value measured now.
Discounted cash flow techniques may be used to evaluate the present value of future cash flows taking account of interest rates and uncertainty.
Cost-benefit analysis techniques and decision trees provide tools for evaluating expected outcomes and choosing between alternative strategies.

## Slide 98: [Chapter 4] Selection of an appropriate project approach 20PW16 KARTHIK MANIAN S

## Slide 99: Objectives
Take account of the characteristics of the system
to be developed when planning a project
Select an appropriate process model
Make best use of the “waterfall” process model
Reduce risks by the creation of appropriate prototypes
Reduce other risks by implementing the project in increments

## Slide 100: Agenda
Project Characteristics
Choosing Technologies
Technical Plan Contents List
Choice of Process Model
Software Prototyping
Categorizing Prototypes
Incremental delivery
Selecting the Most Appropriate Process Model
Conclusion

## Slide 101: Project Characteristics
Technical planning or Project analysis
  All project have certain characteristics
  Methodologies and technologies to be used will be decided for each individual project
  Characteristics for an in-house project
    Project team and users belong to the same organization
    The projects being considered slot into a portfolio of existing computer based systems
    The methodologies and technologies to be used are dictated by local standards

## Slide 102: Project Characteristics …
Reference to step wise approach
  Project characteristics are analyzed at step 3 of stepwise project
  The output of this activity is used by step 4 : Identify the products and activities of the project

## Slide 103: Choosing Technologies
An outcome of project analysis will be the selection of the most appropriate methodologies and technologies
Some of the methodologies
  Object Oriented (OO) development
  SSADM
  JSP (Jackson Structured Programming)

## Slide 104: Choosing Technologies …
The chosen technology will influence the following aspects of the system
  The training requirements for the development staff
  The types of staff to be recruited
  The development environment – both hardware and software
  System maintenance arrangements

## Slide 105: Choosing Technologies …
Analyse other project characteristics
  Is a data oriented or a control oriented system to be implemented?
    ‘Data oriented’ system – will have a considerable database
    ‘Control oriented’ system – embedded control systems
    Uncommon to have systems with components of both types
  Will the software be a general or application specific?
    General package – spreadsheet package
    Application specific – airline seat reservation system

## Slide 106: Choosing Technologies …
  Is the system to be implemented of a particular type for which specific tools have been developed?
    Does it involve concurrent processing?
    Will the system to be created be knowledge –based?
    Will the system to be produced make heavy use of computer graphics?
  Is the system to be created safety – critical?
  what is the nature of the hardware/software environment in which the system will operate?
    The environment in which the final software will operate is different from which it is being developed

## Slide 107: Choosing Technologies …
Identify high level project risks
  Uncertainty can be associated with the products, processes or resources
    Product uncertainty
      Users are uncertain about what the system is to do
      We ask how well the requirements are understood
    Process uncertainty
      Project uses a method (SSAD or OMT) for the first time
      Any change in the way systems are being developed bring uncertainty
    Resource uncertainty
      Uncertainty over the availability of staff
      Depends on the sheer size of the project

## Slide 108: Choosing Technologies …
Select general life cycle approach
  Control systems
    A real-time system will have to be implemented using an appropriate methodology
    Mascot can be used
  Information systems
    SSADM or Information Engineering, that matches the environment
  General applications
    Methodology should be thought of very carefully
    SSADM can be used

## Slide 109: Choosing Technologies …
  Specialized techniques
    Invented to expedite the development of specialized systems
    number of specialized tools and logic based programming languages can be used
    knowledge based system & graphics based system
  Hardware environment
    The environment in which the system is to operate can put constraints on the way it is to be implemented
    Low programming languages can be used

## Slide 110: Choosing Technologies …
  Safety – critical systems
    Safety and reliability are of the essence
    Formal specification using a notation such as Z or VDM
    Calls for expensive measures
  Imprecise requirements
    Uncertainties or a novel hardware/software platform
    Prototyping approach should be considered

## Slide 111
20PW17 KARTHIKEYAN R

## Slide 112: Technical Plan Contents List
The technical plan is likely to have the following contents
  Introduction and summary of constraints:
    Character of the system to be developed
    Risks and uncertainties of the project
    User requirements concerning implementation
  Recommended approach
    Selected methodology or process model
    Development methods
    Required software tools
    Target hardware/software environment

## Slide 113: Technical Plan Contents List …
    Implementation
      Required development environment
      Required maintenance environment
      Required training
    Implications
      Project products and activities – these will have effect on the schedule duration and overall project effort
      Financial – this report will be used to produce costings

## Slide 114
20PW18 KISHOR K R

## Slide 115: Choice of Process Models
“Process” – used to emphasize the idea of a system in action
Executing one or more activities – Process
Activities can be organized in different ways
Can be categorized into different process models
Major part of the planning will be the choosing of the development methods to be used and slotting of these into an overall process model

## Slide 116: Choice of Process Models …
Structured methods
  They are made up of sets of steps and rules
  When rules are applied, they produce system products such as data flow diagrams
  Each of these products is carefully documented
  Usually time consuming compared to others
  Pay-off – less error prone and more maintainable system
  Mostly used in large projects

## Slide 117: Choice of Process Models …
Rapid application development
  Gets working business applications delivered quickly and at less cost
  Adopts tactics such as joint application development (JAD)
  Workshops are conducted where developers and users work together
  Workshops are conducted at clean rooms – free from interruption
  Speeds up communication between users and developers
  Time-boxing – scope of the project is set to meet the deadline

## Slide 118: Choice of Process Models …
The Waterfall Model
Feasibility study
Operation
Testing
Coding
Program design
System design
Analysis
User requirements

## Slide 119: Choice of Process Models …
The Waterfall Model (continued…)
  “Classical” model of system development
  It is an one-shot approach
  There is a sequence of activities working top to down
  The project is expected to progress down the path through each of the phases of development
  Each stage has a deliverable

## Slide 120: Choice of Process Models …
The Waterfall Model (continued…)
  Advantages
    The use of reviews at end of each phase permits acquirer and user involvement
    The model permits early imposition of baselines and configuration control
    Each preceding step serves an approved, documented baseline for the succeeding step

## Slide 121: Choice of Process Models …
The Waterfall Model (continued…)
  Disadvantages
    Customers must be able to express their requirements completely, correctly and with clarity
    Delays can occur in design, coding and testing
    Difficult to access the true stage of progress during the first two to three stages
    No demonstration of system capabilities can occur until the end of the project

## Slide 122: Choice of Process Models …
The V – process model
Feasibility study
Review
User requirements
System design
Program design
code
Program testing
System testing
User acceptance
Corrections
Corrections
Corrections
Corrections

## Slide 123: Choice of Process Models …
The V – process model (continued…)
  Elaboration of the waterfall model
  Stresses the necessity for validation activities
  Each step has matching validation process
  Defects cause a loop back to the corresponding development stage and a reworking of the succeeding steps
  May slip into an ‘evolutionary prototype’

## Slide 124: SPIRAL MODEL
Another way of looking at waterfall model.
Greater level of detail are considered at each stage of the project
Hence greater degree of confidence about the success of the project
More details are analyzed in each sweep and an evolution process is undertaken for next iteration.

## Slide 125: SPIRAL MODEL

## Slide 126
20PW19 MAANASA S

## Slide 127: Software Prototyping
A prototype is a working model of one or more aspects of the projected system.
In order to test assumptions it is constructed and tested quickly and inexpensively.
Classification
  Throw-away prototypes
    Used only to test out ideas and is then discarded.
  Evolutionary prototypes
    It is developed and modified until it is in a state where it can
    become the operational system.
  Incremental prototypes
  The operational system is developed and implemented in small stages so that the feedback from earlier stages can influence later stages of project

## Slide 128: Software Prototyping
Advantages
  Learning by doing.
  Improved communication and user involvement.
  Reduced need for documentation.
  Reduced maintenance costs.
  Production of expected Results.
Disadvantages
  Lack of control and projects standards.
  Additional expense.
  Close proximity of developers.

## Slide 129: Software Prototyping
Other ways of categorizing prototypes
  What is being learnt?
  To what extent is the prototyping to be done?
  What is being prototyped?

## Slide 130: Software Prototyping
What is being learnt?
  Helps to learn about an area of uncertainty in the project.
  Specify what they hope to learn from the prototype
  Plan how the prototype is to be evaluated.
  Report on what has actually been learnt.
To what extent is the prototyping to be done?
  Mock-ups.
  Simulated interaction.
  Partial working model.
  Vertical: some features are prototyped fully.
  Horizontal: All features are prototyped but not fully.
What is being prototyped?
  Human - Computer Interface.
  The Functionality of the system.

## Slide 132: Software Prototyping
Design Increment
Build the increment
Implement the increment
Evaluate the results
Create open technology
plan
Plan increments
Identify system objectives
Feedback
Incremental Delivery Plan
Repeat for each increment
Incremental approach

## Slide 133: Software Prototyping
Advantages
  Feedback from early stages can influence later stages.
  Earlier delivery improves cash flow, because you get some return on investment early on.
  Smaller sub-projects are easier to control and manage.
  ‘Gold Plating’, the requesting of features that are unnecessary should be less as users will know that they get more than one opportunity to make their requirements known.
Disadvantages
  Software Breakage.
  Developers might be more productive working on one large system than on a series of smaller one.
Incremental approach

## Slide 134: Exercise – Incremental Delivery

## Slide 135: Software Effort Estimation
20PW20 MATHIYAZHAGAN S

## Slide 136: CONTENTS
Introduction
When estimates are done?
Problem with over and under estimates
The basis for software estimating
Software effort estimation techniques
Estimating by analogy
Function points
Object points
COCOMO

## Slide 137: Introduction
  Definition of the successful project : The system is delivered ‘on time within budget and with the required quality’.
  Realistic estimates are crucial to the project leader.
  Difficulties in Effort estimation
    Novel Application of software
    Changing Technology
    Lack of homogeneity of Project Experience
    Subjective nature of Estimating
    Political Implications

## Slide 138: Where are Estimates Done?
  Strategic Planning:
  Cost of computerizing potential applications and to decide what priority to give to each project.
  These estimates influence the number of development staff to be recruited by the organization.
  Feasibility Study:
  This ascertains the benefits of potential system will justify the costs.
  System Specification:
  The effort needed to implement different design proposals will need to be estimated.

## Slide 139: Where are Estimates Done? (...)
  System Specification
  Evaluation of Supplier’s Proposals:
  Staff in software houses would need to scrutinize the system specification and produce estimates on which to base proposals.
  Project Planning
  More detailed estimates of smaller work components will be made as the knowledge about the nature of the project increases.
  Estimator will have to speculate about the physical implementation.

## Slide 140: Problems with Under and Over Estimates?
Over estimate will cause the project to take longer time than it would otherwise.
Parkinson’s Law:
‘Work expands to fill the time available’ .which implies that given an easy target staff will work less hard.
Brook’s Law:
The effort required to implement a project will go up disproportionately with the number of staff assigned to the project.
Under Estimate will affect the quality of the Project.
Weinberg’s zeroth law of reliability:
If a system does not have to be reliable , it can meet any other objective.

## Slide 141: Basis for software Estimating
Need For Historical Data:
All estimating methods needs information about how projects have been implemented in the past.
Measure of Work:
To express the work content of the system is to be implemented independently of the effort, using a measure such as source lines of code(SLOC).
Complexity:
Two programs with the same kloc will not necessarily take same time to write, even if it is done by the same developer in the same environment. SLOC estimates have to be modified to take complexity into account.

## Slide 142: Software Effort Estimation Techniques
Algorithmic models
  Which uses ‘effort driver’ representing characteristics of the target system and the implementation environment to predict effort
Expert judgment
  Where the advice of the knowledgeable staff is solicited.
Analogy
where a similar, completed project is identified and its actual effort is used as a basis for the new project.
Parkinson
  Identifies the staff effort available to do a project and uses that as an ‘estimate’

## Slide 143: Software Effort Estimation Techniques (…)
Price to Win
  Where the ‘estimate’ is a figure that appears to be sufficiently low to win a contract.
Top-Down
  The effort needed to implement a project will be related to variables associated with the characteristics of the final system
  effort=(system size)*(productivity rate)
Bottom-Up
Estimator breaks the project into its component tasks and then estimates how much effort will be required to carry out each task. This is done at the later stage of the project.

## Slide 144: Expert Management
  Asking someone who is knowledgeable about either the application area or the development environment to give an estimate of the effort required to carry out a task.
  Estimator would have to carry out some kind of impact analysis in order to judge the proportion of code that would be affected and from that derive an estimate.

## Slide 145: Analogy
  Also called “case based reasoning”
  Identify source cases [project that have been completed
  Identify target cases [project that has similar characteristics
  ANGEL package calculates effort using “Euclidean distance”
  Distance=square-root of((target_parameter1-source_parameter1)2+…..+(target_parameter n –source_parameter n)2)

## Slide 146
20PW21 MEDAM SAI PRANATHI

## Slide 147: Albrecht Function Point Analysis
Top Down Design Method Devised by Allan Albrecht
Albrecht Functional Points – way to Quantify the functional size of programs independent of the programming languages used.
Basis of Function Points – External User Types
    External Input Types
    External Output Types
    Logical Internal File Types
    External Interface File Types
    External Inquiry Types

## Slide 148: Albrecht ..
Each Component is classified as having either high, average or low complexity.
The count of each external user type in each complexity are multiplied by specified weights given in the table to get FP scores.
Identify each instance of each external user type .

## Slide 149: Albrecht Complexity Multipliers
External User Type | Multipliers |  | 
 | Low | Average | High
External Input Type | 3 | 4 | 6
External Output Type | 4 | 5 | 7
Logical Internal File Type | 7 | 10 | 15
External Interface File Type | 5 | 7 | 10
External Inquiry Type | 3 | 4 | 6

## Slide 150: Function points Mark II
The ‘Mark II’ label implies an improvement and replacement of the Albrecht method.
The information processing size is initially measured in unadjusted function points (UFP) to which a technical complexity adjustment can then be applied.
Process
Data Store
Model of a Transaction
input
From user
Return to user
output

## Slide 151: Function points Mark II …
For each transaction the UFP’s are calculated :
      Wi * (number of input data element types) +
      We* (number of entity types referenced) +
      Wo* (number of output data element types) +
Wi , We and Wo are the weightings derived using effort values of previous projects.
From this the average hours of work generated by instances of each type of element is calculated.
The averages are then normalized into weightings which add up to 2.5.
This way of calculating the weightings is time consuming and hence industry averages are available:
Wi=0.58 ; We=1.66 ; Wo=0.26

## Slide 152: Example 1
A cash receipt transaction in the IOE maintenance accounts system accesses two entity types – INVOICE and CASH RECEIPT.
The data elements that are input are
    Date Received
    Invoice Number
    Cash Received
  If an Invoice record is not found for the invoice number, then an error message is issued.If the invoice number is found, then a CASH RECEIPT record is created.
  The error message constitutes the only output data element that the transaction has to cater for.
  The unadjusted function points, using the industry average weightings, for this transaction would therefore be
  0.58*3 + 1.66*2 +0.26*1=5.32

## Slide 154: Object Points
Devised at Leonard N.Stern School of Business, New York University.
Similar to FP approach but takes account of readily identifiable features.
This approach uses the counts of screens, reports and 3GL components
that an application might posses. These components are referred to as objects.
Each object has to be classified as one of the following:
    Simple
    Medium
    Difficult
Based on the classification, complexity weightings are allotted to various object types. [Object Points Complexity Weightings]
The number of objects at each level are multiplied by the approximate complexity weighting shown in the table.
The weighted Sub-totals are then summed tobacco get an overall score for the application.

## Slide 155: Object Points Complexity Weightings
Complexity Weighting |  |  | 
Object Type | Simple | Medium | Difficult
Screen | 1 | 2 | 3
Report | 2 | 5 | 8
3GL Component | - | - | 10

## Slide 156: Object Points …
Some of these objects need not be developed if there are existing components that can be reused.
To take this into account, OP score must be adjusted.
For Example, In an application containing 840 object points, If 20% can be supplied by using existing components, then the adjusted new object points (NOP) score would be:
NOP=840*(100-20)/100=672
Finally, a productivity rate has tobacco be identified using the details of previous projects. [Productivity Rate]

## Slide 157: Productivity Rate
Developer’s experience and capability | Very low | Low | Nominal | High | Very High
PROD | 4 | 7 | 13 | 25 | 50
Person Months needed to carry out the project NOP/PROD = 672/13
= 52 months.

## Slide 158: A Procedural Code-Oriented Approach
Steps to estimate the effort to develop an individual software module
      Envisage the number and type of programs in the final system
      Estimate the SLOC of each identified program
      Estimate the work content, taking into account complexity and technical difficulty
      Calculate the work days effort

## Slide 159: COCOMO
Constructive Cost Model.
COCOMO refers to a group of modules.
Projects are classified to Organic, Semidetached and Embedded.
Based on the type of the project the constant values will vary. [COCOMO Constants]

## Slide 160: COCOMO CONSTANTS
System Type | Values of a | Values of b
Organic | 3.2 | 1.05
Semidetached | 3.0 | 1.12
Embedded | 2.8 | 1.20

## Slide 161: COCOMO CONSTANTS
System Type | Values of c | Values of d
Organic | 2.5 | 0.38
Semidetached | 2.5 | 0.35
Embedded | 2.4 | 0.32

## Slide 162: Steps in COCOMO
STEP 1
Nominal Effort = a * (size )^b
Where size is the number of lines of code in KLOC.
STEP 2
True Effort = Nominal Effort * Product of Cost Drivers
STEP 3
Duration = c*(True Effort) ^d
STEP 4
Effort Distribution for each phase = True Effort * Effort percentage for that phase
STEP 5
Schedule Distribution for each phase = Duration * Duration percentage for that phase.
STEP 6
Manpower = Effort / Distribution

## Slide 163: COCOMO II
Enhanced version of COCOMO.
This approach uses various multipliers and exponents.
In COCOMO II the effort multipliers are similar in nature to the development effort multipliers used in COCOMO.
COCOMO II has models for 3 different stages
        Application Composition
        Early Design
        Post Architecture

## Slide 164: Activity Planning
20PW22 MOHAMED KAIF

## Slide 165
Introduction
A detailed project must include a schedule indicating the start and completion times for each activity.
This chiefly enables us to
    Ensure that the appropriate resources are available.
    Avoid activities competing for the same resource.
    Produce a chart for each activity.
    Produce a detailed plan against which the achievements are measured.
    Produce a cash flow forecast.
    Re-plan the project during its life to correct drift from target.
A plan must have a set of targets.
The achievements are to be measured against these targets.
The starts and completion of the activities must be clearly visible.

## Slide 166
Objectives of Activity Planning
Feasibility assessment: To check for the possibilities that the project will be completed within the estimated time with parameters.
Resource allocation: The most effective ways of allocating resources to the project and when they should be available.
Detailed costing: The cost of the project and a forecast of the likely expenditure.
Motivation: Providing targets and being seen to monitor achievement against targets is a way of motivating staff.
Co-ordination: Synchronize the various activities as and when the project demands.
Activity Planning and scheduling techniques place an emphasis on the timescale and the allocation of the resources.

## Slide 167
When to Plan
Planning is an on-going process of refinement where each iteration becomes more detailed than the previous.
The main purpose of planning will be to estimate the timescales and the risks of not achieving target.
As the project progresses, the emphasis will be placed uopn the production of activity plans.
Monitoring and replanning must continue to correct any drift until the project proceeds to completion.

## Slide 168
Project schedules
The first step in planning is to construct a ideal activity plan.
Ideal Activity plan is a plan of when each activity would ideally be undertaken and where resources are not a constraint.
The ideal activity plan will be a subject of an activity risk analysis, aimed at identifying potential problems.
Next is resource allocation, the expected availability of resources may place constraints on when certain activities may be carried out and our ideal plan may need to be adapted to take account of this.
The final step is schedule production, once resources are allocated to each activity we will be in a position to draw up and publish a project schedule.

## Slide 169
Projects and Activities
Defining activities
Some assumptions that are relevant when we start an activity plan are
  A project is composed of a number of inter-related activities.
  A project may start when atleast one of the activities are ready.
  a project is completed when all the activities are completed.
  An activity must have a clearly defined start and end.
  An activity requires resources that are available to the activity during the project cycle.
  Some activities may require that others are completed before thay can begin (precedence requirements).

## Slide 170
Identifying activities
  two ways of identifying activities, activity-based and product-based approach.
  Activity based approach consists of writing down a list of all the activities. When listing the activities, particularly for a large project, it may be helpful to subdivide the project into the main life-cycle stages and consider each of these separately.
  Product based approach consists of producing a Product Breakdown Structure and a Product Flow diagram and then deriving an ordered list of activities by identifying the transformations that turn some products into others.

## Slide 171
Sequencing and scheduling
We will require a schedule that clearly indicates when each of the project’s activities are planned to occur.
This can be represented with the use of a Bar chart.
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
A: Andy |  |  |  |  |  |  |  |  |  |  |  |  | 
B: Andy |  |  |  |  |  |  |  |  |  |  |  |  | 
C: Andy |  |  |  |  |  |  |  |  |  |  |  |  | 
D: Andy |  |  |  |  |  |  |  |  |  |  |  |  | 
E: Bill |  |  |  |  |  |  |  |  |  |  |  |  | 
F: Bill |  |  |  |  |  |  |  |  |  |  |  |  | 
G: Charlie |  |  |  |  |  |  |  |  |  |  |  |  | 
H: Charlie |  |  |  |  |  |  |  |  |  |  |  |  | 
I: Dave |  |  |  |  |  |  |  |  |  |  |  |  | 
A: Overall Design
B: Specify module 1
C: Specify module 2
D: specify module 3
E: Code module 1
F: Code module 3
G: Code module 2
H: Integration Testing
I : System testing
Approaches to scheduling that achieve this separation between the logical and physical use networks to model the project.

## Slide 172
Network planning models
As mentioned project scheduling activities model the project and their relationships as a network.
In the network time flows from left to right.
The two best known techniques are CPM (Critical Path Method) and PERT (Program Evaluation Review Technique).
Most recently a variation on these techniques called Precedence networks has become popular
All the three methods are popular and have been admitted along by people especially the CPM.

## Slide 173: Critical Path Method
20PW23 PRADIKSHA P
20PW24 PRAVIN BALAJI P R

## Slide 174: Critical Path Method (CPM)
Designed to provide intense micro-control
The system is dynamic; it continues to provide periodic reports as the project progresses

## Slide 175: Manager’s View of CPM
List of project activities
Precedence relationship among activities
Estimate of each activity’s duration
Estimated duration of project
Identification of critical activities
Amount of slack for each activity
CPM processing procedures

## Slide 176: CPM Terminology
Activity
  A task or a certain amount of work required in the project
  Requires time to complete
  Represented by an arrow
Dummy Activity
  Indicates only precedence relationships
  Does not require any time of effort

## Slide 177: CPM Terminology
Event
  Signals the beginning or ending of an activity
  Designates a point in time
  Represented by a circle (node)
Network
  Shows the sequential relationships among activities using nodes and arrows

## Slide 178: CPM Terminology
Path
  A connected sequence of activities leading from the starting event to the ending event
Critical Path
  The longest path (time); determines the project duration
Critical Activities
  All of the activities that make up the critical path

## Slide 179: CPM Terminology
Earliest Start (ES)
  The earliest that an activity can begin; assumes all preceding activities have been completed
Earliest Finish (EF)
  ES + activity time
Latest Finish (LF)
  The latest that an activity can finish and not change the project completion time
Latest Start (LS)
  LF - activity time

## Slide 180: Steps in CPM Analysis
Draw the CPM network
  A graphic view of the relationships among the required activities
Analyze the paths through the network
  Determine the length of each path (time required to complete each path)
  Starting at the beginning of the network and working toward the end (from left to right), determine the ES and EF for each activity
  . . . more

## Slide 181: Steps in CPM Analysis
Path analysis (continued)
  Identify the critical path(s) (the longest path[s] through the network)
  The critical path(s) determines how long the project will take
. . . more

## Slide 182: Steps in CPM Analysis
Determine the slack for each activity
  Working from the end of the project network (from right to left), find the LF and the LS for each activity
  Compute the activity’s slack
  slack = LS - ES = LF - EF
  Slack is the maximum amount of time that this activity can be delay in its completion before it becomes a critical activity, i.e., delays completion of the project

## Slide 183: CPM Example:
CPM Network
a, 6
f, 15
b, 8
c, 5
e, 9
d, 13
g, 17
h, 9
i, 6
j, 12

## Slide 184: CPM Example
ES and EF Times
a, 6
f, 15
b, 8
c, 5
e, 9
d, 13
g, 17
h, 9
i, 6
j, 12
0
6
0
8
0
5

## Slide 185: CPM Example
ES and EF Times
a, 6
f, 15
b, 8
c, 5
e, 9
d, 13
g, 17
h, 9
i, 6
j, 12
0
6
0
8
0
5
5
14
8
21
6
23
6
21

## Slide 186: CPM Example
ES and EF Times
a, 6
f, 15
b, 8
c, 5
e, 9
d, 13
g, 17
h, 9
i, 6
j, 12
0
6
0
8
0
5
5
14
8
21
21
33
6
23
21
30
23
29
6
21
Project’s EF = 33

## Slide 187: Node convention
ES | EF ES+activity time
LS LF-ACTIVITY TIME | LF

## Slide 188: CPM Example
LS and LF Times
a, 6
f, 15
b, 8
c, 5
e, 9
d, 13
g, 17
h, 9
i, 6
j, 12
0
6
0
8
0
5
5
14
8
21
21
33
6
23
21
30
23
29
6
21
21
33
27
33
24
33
ES | EF= ES+activity time
LS= LF-activity time | LF

## Slide 189: CPM Example
LS and LF Times
a, 6
f, 15
b, 8
c, 5
e, 9
d, 13
g, 17
h, 9
i, 6
j, 12
0
6
0
8
0
5
5
14
8
21
21
33
6
23
21
30
23
29
6
21
4
10
0
8
7
12
12
21
21
33
27
33
8
21
10
27
24
33
18
24

## Slide 190: CPM Example
Slack
a, 6
f, 15
b, 8
c, 5
e, 9
d, 13
g, 17
h, 9
i, 6
j, 12
0
6
0
8
0
5
5
14
8
21
21
33
6
23
21
30
23
29
6
21
3
9
0
8
7
12
12
21
21
33
27
33
8
21
10
27
24
33
9
24
3
4
3
3
4
0
0
7
7
0
slack = LS - ES = LF - EF

## Slide 191: CPM Example
Critical Path
a, 6
f, 15
b, 8
c, 5
e, 9
d, 13
g, 17
h, 9
i, 6
j, 12

## Slide 192: Critical Path
There will be atleast one critical path in any network
Any delay to any activity on this critical path will delay the completion of the project
In Project Management, pay attention to critical path activities, so that it is not delayed
If we plan to shorten the overall duration of the project, we have to shorten the critical path activities

## Slide 193
Find the critical path for given project schedule

## Slide 195: Conclusion
We can complete the project in 12 weeks by reducing the duration of activity F by one week i.e. 9 weeks
Suppose activity F is reduced to 8 weeks, calculate the end date of the project
What would be the end date for the project if activity F is shortened to 7 weeks. Why?

## Slide 197
PERT NETWORK
20PW25 RADHAKRISHNAN M
20PW26 RAGHAVAN M

## Slide 198: Evaluating risks to the schedule
The likely effects of risks on planned activities can be identified and categorized – impacts can be assessed
Using PERT to evaluate the effects of uncertainty
  PERT was developed to take account of the uncertainty surrounding estimates of task durations
  Similar to CPM technique
PERT requires three estimates
  Most Likely Time - The time we would expect the task to take under normal circumstances. Denoted by m
  Optimistic Time - The shortest time in which we would expect the task to complete. Denoted by a
  Pessimistic Time – The worst possible time in which we would expect the task to complete. Denoted by b

## Slide 199: Evaluating risks to the schedule- PERT (Contd…)
Using expected durations
  Used to carry out forward pass similar to CPM technique
Activity Standard Deviation
  This SD formula is based on the rationale that there are approximately six SDs between the extreme tails of many statistical distributions
  A quantitive measure of the degree of uncertainty of an activity duration estimate is obtained by using
  s=(b-a)/6
  The activity SD is proportional to the difference between the optimistic and pessimistic estimates and can be used as a ranking measure of the degree of uncertainty

## Slide 200: Evaluating risks to the schedule- PERT (Contd…)
The likelihood of meeting targets
  PERT provides a method for estimating probability of meeting or missing the target dates
  The method used for calculating involves the fillowing steps:
    Calculate the SD o each project event
    Calculate the z values for each event that has a target date
    Convert z values to probabilities

## Slide 201: Evaluating risks to the schedule- PERT (Contd…)
Calculating the SD of each project event
SDs can be calculated by carrying out a forward pass
The only difference is that- to add to SDs their squares must be added and then find out the square root of the sum
Calculating the z values
The z value is calculated for each node that has a target date
It is equivalent to the number of SDs between the node’s expected and target dates by using the formula
z=(T-te)/s
T - Target Date
te - expected date

## Slide 202: Evaluating risks to the schedule- PERT (Contd…)
Converting z values to probabilities
A z value may be converted to probability of not meeting the target date by using a graph
Advantages of PERT
It focuses attention on the uncertainty of forecasting
We can use this technique to find the SD for each task and use this to rank them according to their degree of risk.
By setting target date along the critical path, we can focus on those activities posing the greatest risk to the project’s schedule

## Slide 203: Using PERT to evaluate the effects of uncertainty
Three estimates are produced for each activity
Most likely time (m)
Optimistic time (a)
Pessimistic (b)
‘expected time’ te = (a + 4m +b) / 6
‘activity standard deviation’ S = (b-a)/6
Notes: Most likely time (m) the time we would expect the task to take normally
Optimistic time (a) the shortest time could be realistically be expected
Pessimistic (b) worst possible time (only 1% chance of being worse, say)
Some straightforward activities (data input of standing data might perhaps be an example) might have little uncertainty and therefore have a low standard deviation, while others (software design, for instance?) have more uncertainty and would have a bigger standard deviation.
Exercise 7.6 in the textbook will give some practice in calculating these values.

## Slide 204: PERT Example
PERT activity time estimates, expected times and SDs
Activity duration (Weeks)
Activity Optimistic (a) Most likely (m) Pessimistic (b) Expected (te) SD (s)
5
3
2
3.
1
8
2
2
A
B
C
D
E
F
G
H
6
4
3
4
3
10
3
2
8
5
3
5
4
15
4
2.5
6.17
4.00
2.83
4.08
2.83
10.50
3.00
2.08
0.50
0.33
0.17
0.25
0.50
1.17
0.33
0.08

## Slide 205: PERT Example
PERT network after forward pass
A t=6.17
C t=2.83
H t=2.08
G t=3.00
D t=4.08
B t=4.00
F t=10.5
E t=2.83
1
0
3
4
2
6.17
4
9
6
13.5
5
10.5
Event No.
Target date
Expected Date
SD

## Slide 206: PERT Example
PERT network with 3 target dates and calculated event SDs
A t=6.17
C t=2.83
H t=2.08
G t=3.00
D t=4.08
B t=4.00
F t=10.5
E t=2.83
1
0
3
4
2
6.17
4
9
6
13.5
5
10.5
0
0.50
0.33
0.53
1.22
1.17
15
10
10
s= 0.50
s= 0.33
s= 0.17
s= 0.08
s= 0.25
s= 1.17
s= 0.33
s= 0.50

## Slide 207: Graph of z values
Notes: There is about a 15% chance of not meeting the target of 52 days.

## Slide 210: Monte Carlo Simulation
It is an alternative technique to PERT which provides a greater degree of flexibility in specifying likely activity durations
This technique can be used to evaluate the risks of not achieving deadlines
The basis of this technique is the calculation of event times for a project network a large number of times, each time selecting activity times randomly
Activity durations can be specified in a number of forms, depending upon the information available

## Slide 211: Monte Carlo Simulation for one activity

## Slide 212: Risk Management
20PW27 RAKSHITH U R

## Slide 213: Contents
Introduction
Nature of Risk
Managing Risk
Risk Identification
Risk Analysis
Prioritizing Risks
Reducing Risks

## Slide 214: Introduction
Purpose of Risk Management is to,
decide whether a particular risk is important during completion of project.
evaluate high risk activities on a project’s critical path that are a cause for concern.
Minimize risk, i.e. Minimized over the project and removed from critical path activities.
Common risks in a project include project running late, allocation of staff or the process of identifying risks.

## Slide 215: Nature of Risk
Classified under three broad types,
Estimation Errors: The lack of accuracy in estimation is a common type of risk though predicting with a degree of accuracy might be difficult. Estimation errors can be corrected using historic data for similar projects and activities.
Planning Assumptions: Invalid assumptions may put the plan at risk. At each stage in the planning process, it is important to list explicitly all of the assumptions that have been made and identify the effects that might have on the project.
Eventualities: Some eventualities might never be foreseen and we can only resign the fact that unimaginable things do. Such events do happen from time to time and, although the likelihood of any one of them happening during a particular project may be relatively low, they must be considered and planned for.

## Slide 216: Managing Risk
The objective of risk management is avoid or minimize the effect of the risks.
Barry Boehm suggested Risk Engineering as a model for risk management.
Risk identification: List of all the risks that can adversely affect the successful completion of project.
Risk estimation: Analyzing the likelihood and impact of each hazard.
Risk evaluation: Ranking risks and determining risk aversion.
Risk planning: Drawing contingency plans and adding these to the project's task structure.
Risk control: Functions of the risk manager in minimizing and reacting to problems throughout the project.
Risk monitoring: Ongoing activity to determine risk status.

## Slide 217: Risk Identification
The first stage in risk management is to identify hazards.
An hazard is an event that might occur and will, if it does occur, create a problem for the successful completion of project.
We have to usefully distinguish between the cause (or hazard), its immediate effect of the cause.
A common way of identifying hazards is to use a checklist listing all the possible hazards and factors that influence them.
Risks are of two types, generic risks, relevant to all software projects and standard checklists can be used and augmented from an analysis of past projects. Specific risks are relevant to an individual project and more difficult to identify without the involvement of the team members.

## Slide 218
Factors that will be considered include,
Application Factors: the nature of the application is a critical factor. The expected size is also important with greater being the likelihood for errors when the system is big.
Staff factors: The experience and skills of the staff involved are clearly important to determine the success of the project.
Project factors: Important that the project and its objectives are well defined and that they are absolutely clear to all the members of the team.
Project methods: Usage of well specified and structured methods for project management will decrease the risks in the system.
H/W-S/W Factors: A system developed on one type of h/w and s/w platform to be used on another might be an additional risk to the project.
Changeover factors: Incremental or gradual changeover minimizes the risk involved. Parallel running can provide safety but is too costly.
Supplier factors: The extent to which a project relies on external organizations that cannot be directly controlled influences the project.

## Slide 219
Environment factors: Changes in the environment can affect a project’s success.
Health and safety projects: The effect of the health and safety projects should also be considered though not a major issue for the software projects.

## Slide 220: Risk Analysis
Assessing the importance of the risks once identified.
risk likelihood: The probability of a hazard’s occurrence.
risk impact: The effect of the resulting problem on the project.
risk exposure/value: The importance of the risk.
risk exposure = risk likelihood * risk impact
Risk impact is identified in monetary terms and risk likelihood is assessed as a probability. The estimation of these costs and probabilities is likely to be difficult, subjective, time-consuming and costly.
Easy way is to categorize the likelihoods and impacts as high, medium or low does not need the calculation of risk exposure.

## Slide 221: Prioritizing Risks
Managing risks involves the use of two strategies;
reducing the risk exposure by reducing likelihood or impact.
drawing up a contingency plans to deal with the risk should it occur.
Factors to be taken into account while prioritizing risks are,
confidence of risk assessment: making good judgment.
compound risks: risks dependent on other risks.
number of risks: limit to the number of risks considered.
cost of action: risks can be avoided or reduced with little cost and effort.
Risk Reduction Leverage (RRL),
RRL = Original risk exposure – expected risk exposure
risk reduction cost

## Slide 222: Reducing the Risks
There are five strategies for risk prevention,
Hazard prevention: Some hazards can be prevented or their likelihood reduced to insignificant levels.
Likelihood reduction: Though some risks cannot be prevented their can be likelihood reduced to insignificant levels.
Risk Avoidance: Detailing certain methods to avoid methods and standards to avoid risks.
Risk transfer: The impact of some of the risks can be transferred from the project.
Contingency planning: Some risks are not preventable and contingency plans will need to be drawn to reduce their impact.

## Slide 223
Precedence Network
20PW28 RASHMI N S
20PW30 SAI DINESH B

## Slide 224: Precedence Network
  Precedence Network use boxes to represent activities also known as work items) and links to present dependencies.
  The boxes may carry task description and duration estimates and the links may contain a duration denoting a lag between the completion of 1 task and the start of another.
  The difference between CPM and Precedence Network is that CPM networks use links to represent activities and nodes to represent events.
Advantages of Precedence Network
  They are easier to draw, dummy activities are virtually redundant and also easier to interpret them.
  They can also be used to represent parallel lagged activities

## Slide 225: Precedence Network (continued…)
Activity Label
Duration
Activity Span
1
2
3
4
Activity
Description
The items indicated in the boxes are the same as those shown in the CPM network and the activity table with the addition of Activity span.
Activity Span is the difference between the earliest start date and the latest finish date and is a measure of the maximum time allowable for the activity
Precedence Network will be further discussed in the next chapter
Float
1  Earliest Start Date
2  Latest Start Date
3  Earliest Finish Date
4  Latest Finish Date

## Slide 226
20
IoE/P/1
0
0
34
34
0
34
20
IoE/P/2
34
39
54
59
5
25
15
IoE/P/3
34
44
49
59
10
25
25
IoE/P/4
34
34
59
59
0
25
20
IoE/P/5
34
44
49
59
10
25
7
IoE/P/7
61
61
68
58
0
7
6
IoE/P/8
61
61
67
70
3
9
4
IoE/P/9
61
79
65
83
18
22
4
IoE/P/10
61
69
65
73
8
12
30
IoE/P/11
68
68
98
98
0
30
28
IoE/P/12
67
76
95
98
3
31
20
IoE/P/13
20
30
20
30
20
33
25
IoE/P/14
65
73
90
98
8
33
2
IoE/P/6
59
59
61
61
0
2
6
IoE/P/15
98
98
104
104
0
6
Specify Modules
Check Spec
Design Modules
Coding/Testing Modules
System Integration
Specify Overall System
A
B
C
D
A
B
C
D
A
B
C
D
Blue lines indicate critical activities

## Slide 227
34
IoE/P/1
0
0
34
34
0
34
20
IoE/P/2
34
54
54
54
0
20
15
IoE/P/3
34
44
49
54
5
20
15
IoE/P/5
34
44
49
54
5
20
25
IoE/P/4
34
48
59
73
14
39
7
IoE/P/7
56
56
63
63
0
7
6
IoE/P/8
56
59
62
65
3
9
4
IoE/P/10
56
64
60
68
8
12
4
IoE/P/9
60
74
64
78
14
18
30
IoE/P/11
63
63
93
93
0
30
28
IoE/P/12
62
65
90
93
3
31
25
IoE/P/14
60
68
85
93
20
33
15
IoE/P/13
64
78
79
93
14
29
2
IoE/P/6a
54
54
56
56
0
2
6
IoE/P/14
93
93
99
99
0
6
Specify Modules
Check Spec
Design Modules
Coding/Testing Modules
System Integration
Specify Overall System
A
B
D
C
A
B
D
C
A
B
D
C
Here we decide on a compromise i.e.,A,B and D will be specified together but will then go ahead with their design without waiting for the completion of Module C
2
IoE/P/6a
59
73
60
74
14
15
Blue lines indicate critical activities

## Slide 228
34
IoE/P/1
0
0
34
34
0
34
20
IoE/P/2
34
35
54
55
1
21
15
IoE/P/3
34
34
49
49
0
15
15
IoE/P/4
34
45
49
55
6
21
25
IoE/P/5
49
49
74
74
0
25
7
IoE/P/7
56
57
63
64
1
8
6
IoE/P/8
60
60
66
66
0
6
4
IoE/P/10
56
65
60
69
8
12
4
IoE/P/9
75
75
79
79
0
4
30
IoE/P/11
63
64
93
94
0
30
28
IoE/P/12
66
66
94
94
0
28
25
IoE/P/14
60
69
85
94
9
34
15
IoE/P/13
79
79
94
94
0
15
2
IoE/P/6
54
55
56
57
1
3
6
IoE/P/15
94
94
100
100
0
6
Specify Modules
Check Spec
Design Modules
Coding/Testing Modules
System Integration
Specify Overall System
A
B
D
C
A
B
D
C
A
B
D
C
1
IoE/P/6a
74
74
75
75
0
1
Here we delay the specification of module C for a further day to ensure that only 3-analyst designers are required
Blue lines indicate critical activities

## Slide 229
After converting the activity schedule to work plan, we have to produce a detailed and accurate cost schedule.
The cost schedule can project the weekly or monthly cost and serve as a plan against which project progress can be monitored.
Calculating cost can be straightforward when the organization has standard cost figures for staff and other resources.
In the absence of standard figures, it is the responsibility of the project manager to come up with the cost figures.
Cost Schedules

## Slide 230
Cost are categorized as follows:
Staff Costs – These will include staff salaries as well as other direct costs of employment. These are commonly charges to at hourly rates based on weekly work records completed by staff. Contract staff are usually charged by the week or month even when they are idle.
Overheads – Overheads represent expenditure that an organization incurs, which cannot be directly related to individual projects or jobs. These costs can be recovered by making a fixed charge on development departments or by an additional percentage charge on direct staff employment costs.
Types of Cost

## Slide 231
Usage Charges – In some organizations, projects are charged directly for use of resources such as computer time. This will normally be on an ‘as used basis’.
Types of Cost (continued…)

## Slide 232: A typical Cost Profile
This is a typical cost profile – building up slowly to a peak and then tailing off quite rapidly towards the end of the project
1000
2000
3000
4000
5000
6000
7000
8000
9000
0 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20
Cumulative cost (in Pounds)
Week Number

## Slide 233
1000
2000
3000
4000
5000
6000
7000
8000
9000
Cumulative cost (in Pounds)
Week Number
0 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20
Cumulative Cost of a Project
This cost is generally considered for cost control purposes

## Slide 234: The scheduling sequence
Going from an ideal activity to a costed schedule can be represented as a sequence of steps, rather like the classic waterfall life cycle model.
In the ideal world, we would start with the activity plan and use this as the basis for our risk assessment.
The activity plan and the risk assessment would provide the basis for our resource allocation and schedule from which we produce the cost schedules.
The interplay between the plans and schedules is complex – any change to one will affect each of the others.

## Slide 235
Some factors can be directly compared in terms of money where are others are difficult to express in terms of money terms and will include an element of subjectivity.
While good project planning software will assist greatly in demonstrating the consequences of change and keeping the planning synchronized, successful project scheduling is largely dependant upon the skill and the experience of the project manager in juggling the many factors involved.
The scheduling sequence…

## Slide 236: Conclusion
This chapter discusses the problems of allocating resources to project activities and the conversion of the activity plan to a work schedule. The following point have to be kept in mind during this process:
  Identifying all the resources needed
  Arranging activity starts to minimize variations in resource levels during the duration of the project.
  Allocating resources to competing activities in a rational order of priority.
  Taking care in allocating the right staff to critical activities

## Slide 237: Resource Leveling 20PW38 TAMJID L

## Slide 238
Problem Description
The case that we are considering for the precedence network consists of three main phases i.e. analysis, check specifications and design.
The phases are staffed by four people for the activities A, B, C and D. The activities in the project can be constructed into a precedence network shown in the next slide.
The reason for accommodating resource leveling is that, there might be activities that have float to spare can be delayed corresponding to the float value.
By doing so the resources that had been allocated to the delayed activity can be effectively utilized for the other activities waiting for the resources.
This scenario has been portrayed in the forthcoming slides with precedence networks, bar charts and histograms.

## Slide 239
Based on Precedent Network
STAGE 1
STAGE 2
STAGE 3
STAGE 4
STAGE 5
STAGE 6
IoE/P/6
IoE/P/15
IoE/P/2
IoE/P/3
IoE/P/4
IoE/P/5
IoE/P/7
IoE/P/8
IoE/P/9
IoE/P/10
IoE/P/11
IoE/P/12
IoE/P/13
IoE/P/14
34 days
20 days
15 days
25 days
15 days
2 days
7 days
6 days
4 days
4 days
30 days
28 days
15 days
25 days
6 days
54
59
49
59
59
59
49
59
61
61
68
68
67
70
65
83
65
73
98
98
104
25 days
5 days
25 days
10 days
25 days
0 days
10 days
25 days
2 days
0 days
7 days
0 days
9 days
3 days
22 days
18 days
12 days
8 days
30 days
0 days
31 days
3 days
33 days
18 days
33 days
8 days
6 days
0 days
95
98
80
98
90
98
104
IoE/P/1
0
0
34
34
34 days
0 days
Specify Overall system
Specify
Module
A
Specify
Module
B
Specify
Module
C
Specify
Module
D
Check specs
Design
Module
A
Design
Module
B
Design
Module
C
Design
Module
D
Code/Test
Module A
Code/Test
Module B
Code/Test
Module C
Code/Test
Module D
System integration
34
35
34
44
34
34
34
44
59
59
61
61
61
64
61
79
61
69
68
68
67
76
65
79
65
73
98
98
34 days

## Slide 240: Table 8.1 Part of Amanda’s resource requirement list
Stage Activity Resource Days Quantity Notes
ALL Project Manager 104/FT
1 All Workstation 34 Check software availability
IoE/P/1 Senior Analyst 34/FT
2 All Workstation - 3 1 per person would be ideal
IoE/P/2 Analyst-Designer 20/FT
IoE/P/3 Analyst-Designer 15/FT
IoE/P/4 Analyst-Designer 25/FT
IoE/P/5 Analyst-Designer 15/FT Could use analyst-programmer
3 All Workstation 2/FT
IoE/P/6 Senior Analyst 2/FT
4 All Workstation - 3 As stage 2
IoE/P/7 Analyst-Designer 7/FT
IoE/P/8 Analyst-Designer 6/FT
IoE/P/9 Analyst-Designer 4/FT
IoE/P/10 Analyst-Designer 4/FT
5 All Workstation - 4 1 per programmer
All Office space - if contract programmers used
IoE/P/11 Programmer 30/FT
IoE/P/12 Programmer 28/FT
IoE/P/13 Programmer 15/FT
IoE/P/14 Programmer 25/FT
6 All Full machine access - Approx. 16 hours for full system test
IoE/P/15 Analyst-Designer 6/FT

## Slide 241
STAGE 1
STAGE 2
STAGE 3
STAGE 4
STAGE 5
STAGE 6
IoE/P/6
IoE/P/15
IoE/P/2
IoE/P/3
IoE/P/5
IoE/P/7
IoE/P/8
IoE/P/10
IoE/P/9
IoE/P/11
IoE/P/12
IoE/P/14
IoE/P/13
34 days
20 days
15 days
15 days
2 days
7 days
6 days
4 days
4 days
30 days
28 days
15 days
25 days
6 days
54
55
49
55
49
55
56
57
63
64
62
66
60
69
79
79
93
94
104
21 days
1 day
21 days
6 days
21 days
6 days
3 days
1 day
8 days
1 day
10 days
4 days
13 days
9 days
4 days
0 days
31 days
1 day
32 days
4 days
34 days
9 days
15 days
0 days
6 days
0 days
90
94
85
94
94
94
104
IoE/P/1
0
0
34
34
34 days
0 days
Specify Overall system
Specify
Module
A
Specify
Module
B
Specify
Module
D
Check specs
Design
Module
A
Design
Module
B
Design
Module
D
Design
Module
C
Code/Test
Module A
Code/Test
Module B
Code/Test
Module D
Code/Test
Module C
System integration
34
35
34
40
34
40
IoE/P/4
25 days
74
74
0 days
25 days
Specify
Module
C
49
49
54
55
56
57
56
60
56
65
75
75
63
64
62
66
60
69
79
79
94
94
IoE/P/6a
75
75
1 day
0 days
Check specs
34 days
1 day
Revised Network after delaying module C
74
74

## Slide 242: Bar chart and resource histogram After Delaying module C
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
1
1
Specify overall system
Specify module A
Specify module B
Specify module C
Specify module D
Check Specification
Design module A
Design module B
Design module C
Design module D
Week number
No. of Analysts / designers
Week number

## Slide 243
STAGE 1
STAGE 2
STAGE 3
STAGE 4
STAGE 5
STAGE 6
IoE/P/6
IoE/P/15
IoE/P/2
IoE/P/3
IoE/P/5
IoE/P/7
IoE/P/8
IoE/P/10
IoE/P/9
IoE/P/11
IoE/P/12
IoE/P/14
IoE/P/13
34 days
20 days
15 days
15 days
2 days
7 days
6 days
4 days
4 days
30 days
28 days
25 days
25 days
6 days
54
54
49
54
49
54
56
56
63
63
62
65
60
68
64
78
93
93
99
20 days
0 days
20 days
5 days
20 days
5 days
2 days
0 days
7 days
0 days
9 days
3 days
12 days
8 days
18 days
14 days
30 days
0 days
31 days
3 days
33 days
8 days
29 days
14 days
6 days
0 days
90
93
85
93
79
93
99
IoE/P/1
0
0
34
34
34 days
0 days
Specify Overall system
Specify
Module
A
Specify
Module
B
Specify
Module
D
Check specs
Design
Module
A
Design
Module
B
Design
Module
D
Design
Module
C
Code/Test
Module A
Code/Test
Module B
Code/Test
Module D
Code/Test
Module C
System integration
34
34
34
39
34
39
IoE/P/4
25 days
59
73
14 days
39 days
Specify
Module
C
34
48
54
55
56
56
56
59
56
64
60
74
63
63
62
65
60
68
64
78
93
93
IoE/P/6a
60
74
15 days
14 days
Check specs
34 days
1 day
Revised Network not waiting for module C
59
73

## Slide 244: Not waiting for module C
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
1
1
Specify overall system
Specify module A
Specify module B
Specify module C
Specify module D
Check Specifications
Design module A
Design module B
Design module C
Design module D
Week number
No. of Analysts / designers
Week number
Check Specification C

## Slide 245: Revised for allowing the delay of specifying module C
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
1
1
Specify overall system
Specify module A
Specify module B
Specify module C
Specify module D
Check Specifications
Design module A
Design module B
Design module D
Design module C
Week number
No. of Analysts / designers
Week number
Check Specification C

## Slide 246: Bar chart and resource histogram (After Smoothing)
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
1
1
Specify overall system
Specify module A
Specify module B
Specify module C
Specify module D
Check Specifications
Design module A
Design module B
Design module D
Design module C
Week number
No. of Analysts / designers
Week number

## Slide 247
Monitoring And Control
20PW31 SAMBANTHAM P

## Slide 248
Objectives
Monitor the progress of projects
Access the risk of slippage
Visualize and access the state of a project
Revise targets to correct or counteract drift
Control changes to a project’s requirement

## Slide 249
Introduction
  Once work schedules have been published and the project is under way, attention must be focused on ensuring progress.
  This requires monitoring of what is happening, comparison of actual achievment against the schedule and, where necessary, rivision of plans and schedules to bring the project as far as possible on target.

## Slide 250
Creating the framework
  Exercising control over a project and ensuring that targets are met is a matter of regular monitoring.
  finding out what is happening, and comparing it with current targets.

## Slide 251
  The overall responsibility for ensuring satisfactory progress on a project is often the role of the project steering committee or Project Board.
  Day-to-day responsibility will rest with the project manager and, in all but the smallest of projects, aspects of this can be delegated to team leaders.
  With small projects (employing around half a dozen or fewer staff) individual team members usually report directly to the project manager, but in most cases team leaders will collate reports on their section’s progress and forward summaries to the project manager.
  Reporting many be oral or written, formal or informal, or regular or ad hoc.
Responsibility – key factor

## Slide 252
Steering Committee
Client
Project Manager
Team leader
Team leader
Team leader
Team leader
Analysis/design section
Programming section
Quality Control
section
User documentation section
Project Reporting Structures

## Slide 253
Setting checkpoints
  It is essential to set a series of checkpoints in the initial activity plan. Checkpoints many be:
  Regular (monthly, for example);
  Tied to specific events such as the production of a report or other deliverable.

## Slide 254
Taking snap-shots
  The frequency with which the manager needs to receive information about progress will depend upon the size and degree of risk of the project or that part of the project under their control.
  In general, the higher the level, the less frequent and less detailed the reporting needs to be.

## Slide 255
Collecting the data
  It will still be necessary to gather information about partially completed activities and, in particular.
  forecasts of how much work is left to be completed.

## Slide 256
Partial completion reporting
  Many organizations use standard accounting systems with weekly time sheets to charge staff time to individual jobs.
  The staff time booked to a project indicated the work carried out it charges to the project.
  It does not, however, tell the project manager what has been produced or whether tasks are on schedule.
  Asking for estimated completion times can be criticized on the grounds that frequent invitations to reconsider completion dates deflects attention away from the importance of the originally scheduled targets.

## Slide 257
Weekly time sheets are used for getting information about
work done in addition to time spent
Estimated and scheduled completion dates are also obtained

## Slide 259
Risk reporting
  One popular way of overcoming the objections to partial completion reporting is to avoid asking for estimated completion date, but to ask instead for the team members estimate of the likelihood of meeting the planned target date.
  One way of doing this is the profit light method. This consists of the following steps:
  Identify the key (first level) elements for assessment in a piece of work.
  Break these key elements into constituent elements(second level)
  Access each of the second level elements on the scale green ‘On Target’ , amber for ‘Not on target but recoverable’, and red for ‘Not on target and recoverable only with difficulty’.

## Slide 260
Risk reporting…
  Review all the second level assessments to arrive at first level assessments.
  Review first and second level assessments to produce overall assessment.

## Slide 261
20PW32 SANJITH T
20PW33 SHRIRAM G

## Slide 262
Visualizing progress
  Having collected data about project progress, a manager need some way of presenting data to greatest effect
  Gantt chart
  One of the simplest and oldest techniques for tracking project progress is the gantt’s chart.
  This is essentially an activity bar chart indicating scheduled activity dates and durations frequently augmented with activity floats.

## Slide 264
“Today Cursor” provides immediate visual indication
of which activities are ahead or behind schedule
Figure shows the Gantt chart at the end of Tuesday
of week 17.
“Code and test module D” has been completed ahead
of schedule and “Code and test module A” als appears
to be ahead of schedule.
“Coding and testing “ of other 2 modules are behind
Schedule
THE GANTT CHART

## Slide 266: Gantt charts
Notes: Note that the Gantt chart is named after Henry Gantt (1861-1919) and so should not be written in capitals! You could ask students what they think GANTT stands for before you tell them this to impress this on them. I really find Gantt written as GANTT very, very annoying and threaten students with instant failure of the module if they do this!
The format of the Gantt chart here differs from the format used in Microsoft project as the activities for each team member are grouped together. You could input the details so that they came out in this format, but it would not occur automatically.

## Slide 267
  Slip Chart
Visualizing progress…
  The slip chart is a very similar alternative favoured by some project managers who believe it, provides a more striking visual indication of those activites that are ot progressing to schedule – the more the slip line bends the greater the variation from the plan.
  Additional slip lines are added at the intervals and as they build up, the projectmanager will gain an idea as to whether the project is improving( subsequent slip lines bend less) or not.

## Slide 268
More the slip line bends, the greater the variation from
the plan.
A very jagged slip line indicates a need for rescheduling

## Slide 270: Slip charts
Notes: A slip chart is a version of the Gantt chart where a line is drawn from top to bottom. To the left of the line are all the completed activities and to the right those activities ( or parts of activities) that have not been completed.
The more jagged the line, the more it means that that there are some activities that are lagging to various degrees and some that are ahead of themselves. A very jagged line means that there is scope for re-planning to move resources from those activities that are ahead to those that are behind.

## Slide 271
  Ball chart
Visualizing progress …
  A somewhat more striking way of showing whether or not targets have been met is to use a ball chart.
  In this version of ball chart, the circles indicate start and completion points for activities. The circles initially contain the original scheduled dates. Whenever revisions are produced these are added as second dates in appropriate circles until an activity is actually started or completed when the relevant dates replaces the revised estimate.

## Slide 272: Ball charts
Code and test module A
Code and test module B
Code and test module C
10/10/05
10/10/05
21/10/05
23/10/05
14/10/05
17/10/05
27/10/05
31/10/05
17/10/05
17/10/05
27/10/05
7/11/05
Notes: Circles, which represent the start or finish of activities, start with the initial target dates. If these are modified then the second dates are changed. When the event actually takes place, the colour of the circle is changed to green if it is on target and to red if it has missed the target.
The idea is that this chart is put on a wall in a prominent position as a constant reminder to the project team of the current situation – hence it is often referred to as ‘balls on the wall’.

## Slide 274
The timeline
  One disadvantage of the charts described so far is that they do not show clearly the slippage of the project completion dates through the life of the project.
  The timeline chart is a method of recording and displaying the way in which the targets have been changed throughout the duration of the project.
  Planned time is plotted along the horizontal axis and elapsed time down the vertical axis.
  The lines meandering down the chart represents scheduled activity completion date.

## Slide 275
At the start of the project ‘analyse existing system’ is scheduled
to be completed by the Tuesday of week 3, ‘obtain user
Requirements’ by Thursday of week 5, ‘issue tender’ the final
Activity by Tuesday of week 9 and so on.
At the end of week 2, ‘obtain user requirements’ will not be
completed until Tuesday of week 6 – therefore extends the
activity line to reflect this.
By the Tuesday of week 3, ‘analyse existing system’ is
Completed and a blob is marked on the timeline to indicate
that it is finished.

## Slide 276
At the end of week 4 another three days are
added to the activities ‘draft tender’ and
‘issue tender’
At the end of week 6, two activities have been
completed and three are not completed.
The project as a whole is running 7 days late

## Slide 278: The timeline
Notes: This records the way that targets have changed throughout the project.
Planned time is plotted on the horizontal axis, and actual time on the vertical axis. The bendy lines going from top to bottom represent the scheduled completion date for each activity e.g.
‘analyse existing system’ – at start this was due finish on the Monday of week 3 and it did finish then
‘obtain user requirements’ was originally planned to finish on the Thursday of week 5, but at the end of the first week it was rescheduled to finish on the Tuesday of week 6.

## Slide 279
Cost monitoring
  Expenditure monitoring is an important component of project control. Not only in itself but also because it provides an indication of the effort that has gone into a project.
  A project might be on time but only because more money has been spent on activities than originally budgeted.

## Slide 280
Monitoring earned value
  Having created the baseline budget, the next task is to monitor earned value as the project progresses.This is done by monitoring the completion of task.
  Cost charts become much more useful if we add projected future costs calculated by adding the estimated cost of uncompleted work to the cost already incurred.
  Where a computer based planning tool is used division of cost schedules is generally provided automatically once actual expenditure has been recorded.

## Slide 281
Earned value
  Earned value analysis has gained in popularity in recent years and may be seen as a refinement of cost monitoring.
  Earned value analysis is based on assigning a value to each task or work package (as identified in WBS) based on the original expenditure forecast.
  The assigned value is the original budgeted cost for the item and is known as the baseline budget or budgeted cost of work scheduled(BCWS).

## Slide 282
Earned value…
  Tasks have been started but are not yet complete some consistent method of assigning an earned value must be applied. Common methods in software projects are:
  0-100 technique – where a task is assigned a value of zero until such time it is completed when it is given a value 100 of the budgeted value.
  50 –50 technique – where a task is assigned a value of 50 percent of its value as soon as it is started and then given a value of 100 percent once it is completed.
  Milestone technique – where a task is given a value based on the achievement of milestones that have been assigned values as part of the original budget plan.

## Slide 283
Prioritizing monitoring
  In this section we list the priorities we might apply in deciding levels of monitoring.
  Critical path activities – any delay in an activity on the critical path will cause the delay in the completion date for the project. Critical path activities are therefore likely to have a very high priority for close monitoring.
  Activities with no free float – A delay in any activity with no free float will delay atleast subsequent activities even though the delay is less than the total float it might not delay the project completion date.

## Slide 284
Prioritizing monitoring…
  Activities with less than specified float – If any activity has very less float it might use up this float before the regular activity monitoring brings the problem to the project manager attention.
  High risk activities – A set of high risk activities should have been identified as part of the initial risk profiling exercise.
  Activities using critical resources – activities can be critical because they are very expensive.

## Slide 285
Getting the project back to target
  Shorten the Critical path
  The overall duration of the project is determined by the current critical path, so speeding up non critical path activities will not being forward a project completion date.
  Reconsider the precedence requirements
  Consider the constraints by which some activities have to be differed pending completion to others. The original project network could most probably have been drawn up assuming ideal conditions and normal working practices.

## Slide 286
20PW34 SHYAM S

## Slide 287
Change control
  Configuration librarian’s role
  Control changes and documentations ought to be responsibility of someone who may variously be named the configuration librarian, the configuration manager or project librarian. Among the persons duties would be:
  The identification of all items that are subjected to change control.
  The establishment and maintenance of the central repository of the master copies of all project documentations and software products.
  Settling up and running of formal set of procedures to deal with changes.
  The maintenance of records of who has access to which library item and the status of each librarian item.

## Slide 288
Change control procedures
  A simple change control procedure for operational systems might have following steps:
  One or more users might perceive a need for a modification to a system and ask for a change request to be passed to the development staff.
  The user management consider the change request and if they approve it to the development manager.
  The development management delegate a member of staff to look at the request and to report on the particular practicality and cost of carrying out the changes.
  The development management report back to the user management on the findings and the user management decide whether in view to the cost quoted, they wish to go ahead.

## Slide 289
  One or more developers are authorized to .take copies of the master products that are to be modified
  The copies are modified. In case of software components this would involve modifying the code and recompiling and testing
  When the development of new versions of the product has been completed , the user management will be notified and copies of the software will be released for the user acceptance testing.
  When the user is satisfied that the products are adequate, they will authorize their operational release. The master copies of the configuration items will be replaced.
Change control procedures (contd)

## Slide 290
Changes in scope of a system
  A common occurrence with IS development projects is for the size of system gradually to increase.
  One cause for this is changes to requirements that are requested by users.
  The scope of the project needs to be carefully monitored and controlled. One way is to re estimate the system size in terms of SLOC or function points at key mile stones.

## Slide 291: Managing Contracts
20PW35 SWETHA MURALIDHARAN

## Slide 292: Types of Contract
Supply of completed software:
  A bespoke system, that is, a system developed from scratch for one customer.
  Off-the-shelf, which you buy ‘as is’ – this is sometimes referred to as shrink-wrapped s/w.
  Customized off-the-shelf (COTS) s/w – this is a basic core system, which is modified to meet the needs of a particular customer.
Payment based:
  Fixed price contracts
  Time and material contracts
  Fixed price per delivered unit contracts.

## Slide 294: Fixed Price Contracts
Price is fixed when the contract is signed. If there are no changes in the contract terms, this is the price to be paid on completion of work.
Advantages:
  Known Customer Expenditure.
  Supplier motivation.
  Higher prices to allow for contingency.
  Difficulties in modifying requirements.
  Upward pressure on the cost of changes.
  Threat to system quality.

## Slide 295: Time and Material Contract
The contractor is charged at a fixed rate per unit of effort.
E.g.: salary per hour
Advantages:
  Ease of changing requirements.
  Lack of price pressure.
  Customer liability.
  Lack of incentives for supplier.

## Slide 296: Fixed price per unit delivered contract
Often associated with functional point (FP) counting.
The size of the system to be delivered is calculated and estimated at the outset of the project.
Size is based on lines of code.
Advantages:
  Customer understanding
  Comparability
  Emerging functionality
  Supplier Efficiency
  Life cycle range
  Difficulties with s/w size measurements
  Changing requirements

## Slide 297: More Classification
Based on the approach in selection of contractors:
  Open tendering process
    Any supplier can bid to the supply the goods and services. Furthermore all bids that are compliant with the original condition laid down in the invitation to the tender must be considered and evaluated in the same way as all others.
  Restricted tendering process
    Very similar to open tendering, except that its open only to restricted number of vendors, to submit.

## Slide 298: More Classification…
Negotiated process
  Restricted tendering is not suitable for certain cases.
  E.g. s/w system developed by third party. Customer wants to make certain extensions to it. But the usual tender process in tedious and time consuming.
  So will have to be negotiated with Vendors and resolved.

## Slide 299: Stages In Contract Placement
Requirement Analysis
  Clear set of requirements from the customers
  External Consultant can also be brought to draw up requirements, but the resulting requirements should again be reviewed
  Requirement document (or operational requirement) must include the following
    Functions needed to be carried out
    Input/Output of the functions
    Standards with which there should be compliance
    Quality requirements like response times, reliability, usability and maintainability

## Slide 300
  Each requirement needed to be identified as
  Mandatory: If a proposal does not meet this requirement then the proposal is to be immediately rejected. No further evaluation.
  Desirable : A proposal might be deficient in this respect, but other features of the proposal could compensate for it.
  Requirement Analysis…

## Slide 301
  Draw up plan of how the proposals are to be evaluated
  Specially written systems are evaluated by proposals, for off-the-shelf applications the system itself is evaluated.
  A means of checking the mandatory requirements have to be identified
Evaluation Plan

## Slide 302
  Desirable requirements can be evaluated by weighing the quality of one against the other using standards like ISO 9126
  ‘Value for money’ (price) is also a key criterion for evaluation
  The costs for the whole life time of the system is taken into account
  Evaluation Plan…

## Slide 303
20PW36 SWETHA S

## Slide 304
  Issuing the invitation to tender includes requirement document with a supporting letter involving additional info like deadline etc.
  The invitation to tender is not an offer but an invitation for suppliers to make an offer.
  Customer needs to know the price as well as the way in which the requirements are intended to satisfy (esp. for system developed from scratch)
  In some cases post tender clarifications and negotiations are enough
Invitation to tender

## Slide 305
Two stage tendering process
First stage
  Technical proposals from the suppliers without quotation of price
  Filtering the proposals based on meeting the mandatory requirements
  Discussions with the representative of the selected suppliers with demos and the result of which is Memorandum Of Agreement with each prospective supplier.
Invitation to tender

## Slide 306
  Memorandum Of Agreement is an acceptance by the customer that the proposed solution offered by the supplier meets the requirements.
Second Stage
  Tenders are invited from the suppliers who have signed (MoA) and would be concerned with financial terms of the contract.
  In some cases design should also be proposed and the suppliers would be paid for it.
  Final contract is awarded to the most attractive proposal
Invitation To tender…

## Slide 307
Done in a methodical and planned manner
Different type of evaluation patterns for different applications
System itself is evaluated for off-the-shelf systems, proposals evaluated for bespoke systems, both system and proposal for COTS
Evaluation of Proposals

## Slide 308
The process of evaluation may include
Scrutiny of the proposal documents: It involves reviewing the proposal documents whether they meet the requirements, clarification on certain points, legal issues.Written, agreed record can be sought.The terms of the contract has to be scrutinized to check the supplier has not excluded pre contract negotiations.
Interviewing suppliers representatives
Evaluation of Proposals…

## Slide 309
Demonstrations: Demos on the mandatory features can be given by suppliers
Site visits: Features like platform dependency could be checked by visits to operational sites.
Practical tests
There can be contract department in the organization to check for the correct procedures and legal format of the contract could be checked by a legal expertise.
Evaluation of Proposals…

## Slide 310: Typical terms of Contract
Definitions:
  Terminology used in the contract document may be defined, example the words ‘client’ and ‘supplier’
Form of agreement
  Is it a contact of sale, a lease, or a license.
Goods and service to be supplied
  All hardware and equipments needed are delivered.
  Services like, training, documentation, installation, maintenance agreement.
Ownership of the S / W
  Decision on who owns the software. Certain contracts for a particular user, the users owns the license. Else the contractor takes care of the ownership.

## Slide 311: Terms of contract cont…
Environment
  Where physical equipments are to be installed. They include accommodation, electrical supply and h/w and operating system for the s/w.
Customer commitment
  Basic and general facilities had to be provided by the customer.
Acceptance procedure
  Accept a delivered system only after it has under gone the user acceptance testing.
Standards
  Standards with which the goods and services should comply.
  E.g. ISO 12207 talks about standards regarding the s/w life cycle and documentation.

## Slide 312: Terms of contract cont…
Project and quality management
  Arrangements for the management of the project must be agreed.
  Contract should require the appropriate ISO 9000 series standards
Timetable
  Provides a schedule of when the key parts of the project should be completed.
Price and payment method
  Supplier’s desire to be able to meet the costs as they are incurred needs to be balanced by the customers requirement to ensure that goods and services are satisfactory before parting with money.

## Slide 313: Managing People and Organizing teams
20PW37 HARINI SHRI T
20PW39 TRISHA M

## Slide 314
Introduction
Project leader can encourage effective group working and decision making while balancing this,where needed,by purposeful leadership.
Although perhaps having little control over organizational structure, the project leader needs to be aware of its implications.
The scope and nature of activities can be set in a way that will enhance staff motivation.
Many risks to project success relate to staffing.
The qualities of individual members of staff should be taken into account when allocating staff to activities.

## Slide 315
Understanding behaviour
Handling of people is one of most important aspects of project management.
OB(Organizational Behaviour) has evolved theories that try to explain people’s behaviour and that tend to be structured ‘If A is the situation then B is likely to result’.
Attempt are then made to observe behaviour where variables for A and B are measured and a statistical relationship between the two variables is sought.
In real world, it is difficult to decide which set of research findings is relevant.

## Slide 316
Organizational behaviour:a background
Taylor has three basic objectives:
To select the best person for the job;
To instruct such people in the best methods;
To give incentives in the form of higher wages to the best workers.
‘Taylorism’ is often represented as crude and mechanistic these days.

## Slide 317
Organizational behaviour:a background…
State of mind of workers influence their productivity.
Theory X
The cash-oriented view of work of some managers.This attitude is labelled as Theory X,which holds that:
The average human has an innate dislike of work;
There is a need therefore for coercion,direction and control;
People tend to avoid responsibility.

## Slide 318
Organizational behaviour:a background…
Theory Y
People in their place of work.This attitude is labelled as Theory Y,which holds that:
Work is as natural as rest or play;
External control and coercion are not the only ways of bringing about effort directed towards the company’s ends;
Commitment to objectives is a function of the rewards associated with their achievement;
The average human can learn to accept and further seek responsibility;
The capacity to exercise imagination and other creative qualities is widely distributed.

## Slide 319
Selecting the right person for the job
One of the biggest differences in software development performance is between individuals.
What sort of characteristics should the company look for? Should they go for experienced programmer or new graduate?
It is dangerous to generalize but American researcher Cheney found that the most important influence on programmer productivity seemed to be experience.

## Slide 320
A general approach:
Create a job specification
Formally or informally the requirements of the job need to be documented.
Create a job holder profile
Using the job specification, a profile of the sort of person who would be needed to carry out the job is constructed.
The recruitment process

## Slide 321
Obtain applicants
Advertisements with enough information would be placed to allow an element of self-elimination and to obtain realistic candidates.
Examine Curricula vitae
CV should be read carefully and compared with the job holder profile.
Interviews
A number of selection techniques can be adopted. Formal scoring system for the qualities being judged should be devised. Interviews can be either technical or general.
The recruitment process…

## Slide 322
20PW40 VIJAY KRISHNA D

## Slide 323: Instruction in the best methods
When a new member of the team is recruited, the team leader need to plan his induction very carefully.
Team leader should assess the training needs of his team members.
Training needs profile is drawn up for each staff before considering specific courses.
The methods learnt during the training need to be actually applied. Reviews and inspections should help to ensure this.

## Slide 324: Motivation
There are several models of motivation.
The Taylorist model
Taylor’s viewpoint is reflected in the use of piece-rates in manufacturing industries and sales bonuses amongst sales force.
Radical changes in work practices have to be preceded by a move from piece-rates to day-rates.
In a company, a reward system that makes excessive distinctions between co-workers can be damaging to morale and eventually to productivity.

## Slide 325: Motivation…
Maslow’s hierarchy of needs
Abraham Maslow, a an American psychologist, suggested that there is a hierarchy of needs.
As lower level of needs are satisfied then gradually higher level needs will emerge.
Project Leader must realize that people are likely to be motivated by different things at different stages of their life.

## Slide 326: Motivation…
Herzberg’s two-factor theory
Certain things about a job might make the employee dissatisfied. If the causes of this dissatisfaction are removed, this does not necessarily make the job more exciting.
Hygiene or maintenance factors
The level of pay or the working conditions;
Motivators
These make the employee feel that the job is worthwhile, like a sense of achievement or the nature of work itself.

## Slide 327: Motivation…
The expectancy theory of motivation
A model developed by vroom and his colleagues identifies three influences on motivation:
Expectancy
the belief that working together will lead to a better performance;
Instrumentality
The belief that better performance will be rewarded;
Perceived value
perceived value of the resulting reward.
Motivation will be high when all three factors are high. A zero level for any one of the factors can lead to a lack of motivation.

## Slide 328: Motivation…
The Oldham-Hackman job characteristics model
Satisfaction of a job is based on five factors.
Skill variety
The number of different skills that the job holder has the opportunity to exercise;
Task identity
The degree to which your work and its results are identifiable as belonging to you;
Task significance
The degree to which your work and its results are identifiable as belonging to you.

## Slide 329: Motivation…
Autonomy
The discretion you have about the way that you do the job;
Feedback
The information you get back about the results of your work.
In practical terms, activities should be designed so that, where possible, staff follow the progress of a particular product and feel personally associated with it.

## Slide 330: Methods of improving motivation
Setting specific goals
Involving staff in the setting of goals helps to gain acceptance for them.
Providing feedback
Not only do the goals have to be set but staff have to have regular feedback about how they are progressing.
Job design
Jobs can be altered to make them more interesting and give staff more feeling of responsibility.

## Slide 331: Methods of improving motivation…
Two measures are often used to enhance job-design.
Job enlargement
The scope of the job is increased so that the member of staff carries out a wider range of activities.
Job enrichment
Job is changed so that the holder carries out tasks that are normally done at a higher, managerial level.

## Slide 332: Working in groups
Any software project involves working in groups which many people find it difficult.
Formal groups can be subdivided into command groups.
Command groups are departmental groupings which reflect the formal management structure
Task groups set up to deal with specific tasks. they call on people from different command groups and would typically be disbanded once the task has been completed.

## Slide 333: Becoming a team
Teams go through five basic stages of development:
Forming-the members of the group get to know each other and try to set up some ground rules about behaviour.
Storming- conflicts arise as various members of the group try to exert leadership and the group’s methods of operation are being established.
Norming-conflicts are largely settled and a feeling of group identity emerges.
Performing-the emphasis is now on the tasks at hand.
Adjourning-the group disbands.
According to belbin,a team needs a balance of different types of people

## Slide 334: Becoming a team…
The chair -leader good at running meetings,calm,strong but tolerant
The plant -very good at generating ideas and potential solutions for problems
The monitor-evaluator good at evaluating ideas and helping to select the best one
The shaper-helps to direct the team’s attention to the important issues
The team worker-skilled at creating a good working environment
The resource investigator-finding resources in terms of both physical resources and information
The completer-finisher-Good at completing tasks
The company worker-A good team player who is willing to undertake less attractive tasks if hey are needed for team success

## Slide 335: Becoming a team…
To be a good team member :
    time your interventions
    be flexible
    be restrained
    keep the common goals of the team in mind all the time
Group Performance
A manager of IBM was quoted as saying:' Some work yields better results if carried out as a team while some things are slowed down if the work is compartmentalized on an individual basis’.

## Slide 336: Becoming a team…
Group tasks can be categorized into
Additive tasks-are where the efforts of each participant are added together to get the final result.
  Compensatory tasks-the judgements of individual group members are pooled so that errors by some group members are compensated for by the inputs from others.
Disjunctive tasks-the effectiveness of the group depends on:
    someone coming up with the right answer.
    the others recognizing it as being correct.
Conjunctive tasks-are where progress is governed by the rate of the slowest performer. The overall task is not completed until every participant's work is complete.

## Slide 337
20PW01 ABISHEK A

## Slide 338: Decision making
Decisions can be categorized as being
Structured-simple, routine decisions where rules can be applied in a straightforward way
Unstructured-more complex and often requiring a degree of creativity
Some mental obstacles to good decision making
Faulty heuristics-Heuristics means rules of thumb. There are dangers in it.
They are based only on information that is to hand and this can be misleading.
They are based on stereotypes.

## Slide 339: Decision making…
Escalation of commitment-once a decision is made it is increasingly difficult to alter it even in the face of evidence that it is wrong.
Information overload-presenting with too much data is also a mental obstacle for good decision making.
Group Decision Making
  With a project team, different specialists and points of view can be brought together.
  Research show that groups are better at solving complex problems where the members of the group have complementary skills and expertise.

## Slide 340: Decision making …
  Groups are less effective when dealing with poorly structured problems, which needs creative solutions.
  Prototyping and participatory approaches such as JAD(Joint Application Development) might be adopted to get the involvement of the end users
  Obstacles to good group decision making
  Some drawbacks are,
    It is time consuming.
    It can stir up conflicts within the group.
    Decisions can be unduly influenced by dominant members of the group.
    People will modify the personal judgements to conform to group norms.
    People in a group often make decisions that carry more risk than when they have to make the decisions on their own. This is called as risky shift.

## Slide 341: Decision making …
Measures to reduce the drawbacks of group decision making
The Delphi technique makes this more efficient by training members to follow a set of procedure. The following is the procedure:
The cooperation of a number of experts is enlisted
The problem is presented to the experts
The experts record their recommendations
These recommendations are collated and reproduced
The collected responses are recirculated
The experts comment on the ideas of others.
If the leader detects a consensus then the process is stopped, otherwise comments are recirculated to the experts

## Slide 342: LEADER SHIP STYLES

## Slide 344: Leadership
Leadership is based on some kind of authority or power, although leaders do not necessarily have much formal authority.
This power comes from either the person’s position(position power) or from the person’s individual qualities(personal power)
Position Power is further analysed as
coercive power-the ability to force someone to do something by threatening punishment
connection power-which is based on having access to those who have power
legitimate power-which is based on a person’s title conferring a special status
reward power-where the holder can confer rewards on those who carry out tasks to their satisfaction

## Slide 345: Leadership…
Personal power can be analysed into
Expert power-which comes from being the person who is able to do a specialized task
Information power-where the holder has access to information that others do not
Referent power-which is based on the personal attractiveness of the leader
Leadership styles
It is measured on two axes: directive vs. permissive and autocratic vs. democratic.
Directive autocrat-makes decision alone with close supervision on their implementation
Permissive autocrat-makes decision alone but gives subordinates latitude in implementation.

## Slide 346: Leadership…
Directive democrat-makes decisions participatively but closely supervises their implementation.
Permissive democrat-makes decisions participatively and gives subordinates latitude in implementation.
A manger will either be task oriented or people oriented.
task oriented-extent to which the execution of the task at hand is paramount. where there is a high degree of uncertainity ,subordinates will seek guidance from above and welcome a task oriented management style.
people oriented-degree to which the manager is concerned about the people involved. People oriented managers are better where staff can control the work they do and know what to do without referring matters to their line managers.

## Slide 347
20PW02 AKASH A

## Slide 348: Organizational structures
Formal versus informal structures
The formal structure is the one that is expressed in the staff hierarchy chart, concerned with authority.
Informal structure of contacts and communication that grows up spontaneously among members of staff during the course of work.
Hierarchical structure
Based on the concept of hierarchy. Authority flows from top down through the structure.
Span of control-the number of people that a manager can effectively control

## Slide 349: Organizational structures…
Staff versus line
Staff can be subdivided into line workers who actually produce the end product and support staff who carry out supporting roles.
In a software company, software specialists might be seen as a part of the line.
In a financial organization, the information systems department can be seen a part of the support staff.
Controlled decentralized groups
A project team is made of groups under the leadership of senior programmers.
Within the group there is free communication and a practice of reviewing each others work.

## Slide 350: Organizational structures…
Egoless programming
Gerald Weinberg made the revolutionary suggestion that programmers and programming team leaders should read other people’s programs.
Programs would become in effect the common property of the programming group and programming would become egoless.
Peer code reviews are based on this idea
Chief programmers team
The chief programmer is the person who defines the specialisation,and designs,codes,tests and documents the software.
Copilot-with whom the chief programmer can discuss problems and who writes some code.
They are supported by an Editor who writes up the documentation drafted by the chief programmer and Program clerk who maintains the actual code ,and a Tester
Problem is getting hold of really outstanding programmers to carry out the chief programmer role.

## Slide 351: Organizational structures…
Centralized versus decentralized group structures
In a decentralized organization group members would tend to make major decisions collectively and there would be a larger degree of free communication among group members
Decentralized group tend to work slowly. They are affected by the establishment of group norms and the influence of risky shift. But they are better at dealing with complex problems
With centralized approach, the group would be broken down into sections. each of which would be directed by a leader.
It deals more effectively with simple problems.

## Slide 352: Organizational structures…
Departmentalization
Functional departmentalization
System analysts might be put in a group separate from the programmers. Programmers would act as a pool from which resources may be drawn for particular tasks.
It can lead to a more effective use of staff.
It also makes it easier for programmers to have careers that are technically oriented
Drawback is that two separate departments can lead to communication problem and also problems with software maintenance
Task oriented approach
Programmers and system analysts are grouped together in one project team.
The project team might be gathered to implement a specific long term project or to service the needs of a particular set of users

## Slide 353: Organizational structures…
Life cycle phase
A departmentalization where there are separate teams for development and maintenance.
Some staff concentrate on developing new applications while other teams more oriented towards service and support, deal with maintenance.
Matrix Structure
The programmer would have two managers-a project leader who would give day-to-day direction about the work in hand.
A programming manager who would be concerned about such things as career development.

## Slide 354: SMALL PROJECTS
20PW03 AKSHAYA J

## Slide 355
Introduction
One of the problem faced by the students when
planning projects is lack of knowledge in applying
techniques learned in software project.
This chapter present an outline of how the students
should set out their Project plan.

## Slide 356
Some problems with student projects
Some problems or risks that seem particularly to affect student projects as follows
        Use of unfamiliar tools.
        Uncertain design requirements
        Incomplete systems.
        Lack of commitment from clients.

## Slide 357
Use of unfamiliar Tools
Use of unfamiliar tools during project development will halt or delay the project progress
To avoid this either familiar tools have to be used or proper time have to be allocated on studying the tool.
The risk of technical problems will be reduced if proper software tools are used.

## Slide 358
Uncertain design requirements
Project assignments require students to carefully perform analysis and design of the project.
Example: If 10 weeks is allocated for the project then it should follow the following schedule
      Weeks 1-2:Analysis
      Weeks 3:Design
      Weeks 1-2:System building
      Weeks 1-2:Testing and evaluation
Actual breakdown will vary depending on the circumstances of a particular project.

## Slide 359
Uncertain design requirements…
Have to prepare to delay planning a particular phase of a project until more information become available in detail.
The scope of the application has to be cut down to fit the available time.

## Slide 360
Incomplete Systems
Sometimes students simply run out of time and so
do not have a working system to demonstrate.
To avoid that the following schedule can be used which break down the work into increments
      Weeks 1-2:Analysis
      Weeks 3:Design increment 1
      Weeks 4:Build/Test increment 1
      Weeks 5:Design increment 2
      Weeks 6:Build/Test increment 2
      Weeks 7:Design increment 3
      Weeks 8:Build/Test increment 3
      Weeks 9:Evaluate complete system
      Weeks 10:Writing up/contingency

## Slide 361
20PW04 ANIRUDH BALAKRISHNAN

## Slide 362
Content of the project plan
In this section we shall discuss what should be there in the project planning document .It is suggested that the plan for small projects being done for outside clients should follow
the following formats.
        Introduction
        Background
        Objectives of the projects
        Constraints
        Methods/technology to be used
        Project products
        Activities
        Resources
        Risk analysis

## Slide 363
Content of the project plan
INTRODUCTION
The introduction to the project plan should include the following
        Identity of clients
        Short description of project
        Objectives of the projects
        Identity of the project authority

## Slide 364
Content of the project plan
BACKGROUND
This includes
        Relevant information about the client’s business
        Description of the existing software/hardware environment
        Circumstances or problems leading to the current project
        Work already carried out in the area of the project
        Stakeholders in the projects

## Slide 365
Content of the project plan
OBJECTIVES OF THE PROJECT
It might be already have been defined in terms of reference document.
The objectives must define what is to be achieved and the method of measuring the extent of that achievement.
This document is the part of benefit of the client, the objectives from the client’s viewpoint should have the emphasis here. Circumstances or problems leading to the current project
Students should recognize the distinction between the project objectives and their personal objective
In case of several objectives an order of priority should be given to them.

## Slide 366
Content of the project plan
CONSTRAINTS
This is convenient to merge this into the project objective .Constraints includes
      Externally imposed time scales
      Legal requirements
      Specific standards
      Limitations on the people who can be approached for information

## Slide 367
Content of the project plan
METHODS/TECHNOLOGY TO BE USED
The part of the projects will involve the selection of most appropriate technologies and methods
some cases it is needed to specify the general approach
for instance the use of SSADM or SSM approach.
The training and other resource requirements that result from the decisions should be noted.

## Slide 368
PROJECT PRODUCT
    This is a list of all the products or deliverables that the project will produce, such as software modules, documentation, user guides and reports
    Intermediate products, such as design documents , should be included
Content of the project plan

## Slide 369
ACTIVITIES
This is a list of the main activities that the project will involve.
For each activity, define
    Pre-requisites
    Dependent activities
    Estimated time/effort
    Quality checks
    PERT or Gantt charts may be used but are often not needed
Content of the project plan

## Slide 370
RESOURCES
This includes staff time, accommodation and hardware/software requirements .
RISK ANALYSIS
Identify the main things that can be seen as possible going wrong. This includes
    Unavailability of resources
    Unavailability of key client personnel
    Technical problems
A priority can be given to each risk by allocating a probability rating(1-10) .Multiplying the two together gives an overall
Score for priority purpose
Content of the project plan

## Slide 371
Take care when using techniques or tools that are completely new to the project
Students should have to adjust the scope of the project to fit the time available
Take steps to maintain the commitment of the client to the students ‘free’ project
Recognize the distinction between the project objectives and the students personal objective
Avoid planning activities for which there is no tangible result – like ‘familiarization’
Conclusion

## Slide 372: Case Study Exercise

## Slide 373
Case Study – 1
Title: THE PROJECT WAS THREE YEARS LATE: BUT AN INCREDIBLE SUCCESS!!
It started like any other project. We had a scope statement, a diverse team, a list of interested contractors, and the enthusiastic support of management. We even had binders with an indexed list of the plans deemed essential for successful projects: communication, change management, risk management, and all the others. And although we had challenging cost and schedule requirements, we knew we had an excellent plan. Nothing could prevent us from delivering this project on time and under budget. At least, that is what we thought!

## Slide 374
Case Study – 1...
We had hardly started when trouble struck. The first hint of a problem came in the form of questions about our spending curve. The company was concerned about its overall capital spending and it was looking for opportunities to delay major expenditures into the next fiscal year. We were able to oblige initially. We reassessed our schedule and proudly offered a new plan with the most expensive scope deferred to late in the project. The best news was that we would still meet our original cost and schedule commitments.
Our excitement was short lived. No sooner had we submitted our new plan than we were asked to reduce our early spending even more. In fact, each new plan drew the same request. Eventually, we had to admit we could no

## Slide 375
Case Study – 1...
longer complete the project on time. That is when the second
blow struck. We were informed the project was no longer a
top priority. In fact, some members of management were
advocating our project be canceled. Morale within the
project team plummeted to a new low. Just a few short
weeks earlier, our project had been priority #1. Success was
guaranteed. Now we were on the verge of being shut down.
Our project was intended to increase production by
modifying each of our 21 paper machines at four
manufacturing plants located throughout the USA. Generally,
we were to install control devices designed to reduce defects
and allow us to speed up the machines. Some of the
technology was new, even unproven, but our technical
experts assured us it would work as intended.

## Slide 376
Case Study – 1...
“A no brainer” they called it. And so we had developed a
comprehensive list of which devices were to be installed on
which machines, and how much additional production we
could expect from each.
However, our sales volume was not developing as
anticipated. And as disappointing monthly sales reports
continued to accumulate, management became increasingly
reluctant to spend any money on increasing production.
Eventually we were ordered to put the project on hold, but to
be ready to restart at any moment.
It was time for a new strategy. And since we were no
longer under a time constraint we decided to reduce our risk
by prototyping each of the technologies included in the original
scope. We installed and tested each device on a different

## Slide 377
Case Study – 1...
paper machine. To our surprise, some did not work as
intended. They were not the key to increasing the production
rate we expected. Some even had the opposite effect. They
produced unintended side effects that caused a decrease in
production. But fortunately, not all were failures. Some
worked much better than we expected, enabling us to
increase the production rate by two or three times the amount
we had initially estimated.
The obvious solution at this point was to modify our
scope. Clearly, we could achieve the same overall production
increase by just installing the devices that worked better than
expected and abandoning the others. But an even better
strategy began to emerge. As the technical experts analyzed
the results of our prototypes, new ideas arose. The experts

## Slide 378
Case Study – 1...
identified modifications that could work even better than the
devices that had proven successful. And so we prototyped
these ideas too. And as we now expected, some worked and
some did not. And the results prompted even more ideas.
Eventually, the company’s sales began to recover and
management started asking for increased production. By this
time, we had a menu of proven technologies ready for
installation. And we were therefore able to quickly reapply the
modifications that provided the best return on investment.
But we now had a proven strategy and we resisted the
temptation to deviate. We continued to encourage new ideas,
but then insisted on testing them on a single paper machine
before declaring them ready for reapplication.

## Slide 379
Case Study – 1...
We eventually ran out of money five years after the
project was initially authorized, and more than three years
after our original completion date. But by this time, we had
added three times the production increase we had initially
promised. We still had to complete all the paper work to
changed the scope and missed our completion date, of
course, but nobody really cared. The real project objective
was to increase production at an affordable cost, and we had
succeeded beyond our wildest dreams.
Real evidence of success came when the company
asked us to submit the paper work to initiate another project.
This time, we admitted our scope was a guess and sure to be
wrong. But management did not care. They just told us to
continue with the same approach, and gave us the amount we

## Slide 380
Case Study – 1...
requested. It was the easiest project approval I ever
experienced.
Clearly, if we had treated this as a traditional project we
would have failed. We would have achieved our initial cost
and schedule commitments, but produced only a fraction of
the production increase we promised. Fortunately, unexpected
problems arose and we were forced to develop a strategy
much more appropriate for the situation. And we delivered
what the company really wanted: additional production at an
affordable cost.

## Slide 382
Case Study – 2
Title: Learning from Experience
Dr. Alex Laufer
I was confused and didn't know how to react when Jim
Carroll, proudly presented me with his "Nine Elements for
Project Success," the product of two years arduous labor.
These nine elements were presented as a well-accepted
model, as if they were based on solid findings, and were
meant to serve as guidelines for the successful management
of capital projects. To my mind, however, the nine elements
were based on weak hypotheses and were clearly deficient.
Jim, President of Flour Daniel/Morrison Knudsen, LLC,
was at the time, February 1988, serving on the Construction
Industry Institute (CII) Project Organization task force. When I
was first invited to join this task force, it was just after it had

## Slide 383
Case Study – 2...
experienced a breakthrough. In one of its most productive
meetings, the task force was able to identify the "Nine
Elements for Project Success." The task force then appointed
a small team of five members, headed by Jim, to produce a
handbook for practitioners that would thoroughly explain each
of these nine elements.
I just could not accept the "Nine Elements for Project
Success." First, they did not cover very important areas of
capital projects. Second, they were stated as the "one-best-
way" principles, completely ignoring the rich variety of project
contexts stemming from the different environments,
organizations, technologies, projects, and people.
There was another issue complicating the matter for me.
I came to the CII with the understanding that I was expected

## Slide 384
Case Study – 2...
to conduct research for them. I did not feel that my
accumulated theoretical research findings allowed me to
prepare a chapter useful for practitioners.
I spent a full three hours talking with Jim. To be more
accurate, I should say arguing and debating with him, often
quite heatedly. At first he stonewalled me. I could not produce
the tiniest dent in his rock-hard opinion. Jim stubbornly
maintained that applying these nine elements was the way,
and the only way, to achieve project success. After all, it took
the task force two years to agree on these elements, and Jim
was clearly in no mood to retreat and re-examine them. He
wanted to make further progress and bring back to the task
force tangible products, that is, finalized chapters of the
handbook.

## Slide 385
Case Study – 2...
It was close to midnight when I realized that I would
never be able to convince Jim of the weakness of the nine
elements, and was almost about to give up. As a last resort, I
asked him whether he would be ready to put the nine
elements to a personal test. That is, I asked him to see
whether the application of the nine elements could explain the
success or failure of the projects with which he was involved
during his career. Jim confidently agreed to put the elements
to the test.
The next day, the entire five-member team received a
fax from Jim in which he shared a simple analysis of the
seven projects with which he was involved during his career.
He rated the projects according to their success -- four
projects were rated successes and three were rated failures.

## Slide 386
Case Study – 2...
He also examined whether the nine elements applied to those
projects. Now it was Jim's turn to be confused.
There was very little, if any, apparent correlation
between project success and the nine elements. For example,
some elements were applied to all seven projects, and some
almost to none. Two factors exhibited a most bizarre behavior.
They applied to all the failed projects, but they did not apply to
all the successful ones.
Jim is an unusually courageous man. He was willing to
reflect on his experience and to learn from it, or more
accurately in our case, to unlearn from it, and to share his
unlearning with us. He was willing to admit that the nine
elements could not provide the complete answer. I was very
satisfied; especially in light of the fact that now I felt I was able

## Slide 387
Case Study – 2...
to conduct a study within the CII organizations before
attempting to write my chapter.
Denying Uncertainty
But my problems with the task force were not over yet. A
year later, I submitted my research report to the task force.
The results, based on an elaborate study in 11 CII member
companies, were quite shocking to most members of the task
force. Among other things, my findings showed that in most
capital projects, uncertainty is not resolved early in the life of
the project, for example, at the end of project design. Even
more troubling was my finding that in most capital projects, not
only are the "means uncertainty" (how to do it) resolved late in
the project life, but so are the "end uncertainty" (what to do).

## Slide 388
Case Study – 2...
Since most members of the task force could not accept
that capital projects suffer from uncertainty, and definitely not
from "end uncertainty," they adjusted the presentation of my
findings. Instead of portraying project planning as a gradual
process of lessening uncertainty, they portrayed it as a
gradual process of increasing certainty.
The task force's behavior at the conclusion of my study
was very much in line with, and may even explain, their
behavior from the outset of the study. The task force members
felt comfortable in a certain world, and so they denied
uncertainty, even in the face of empirical data from within their
own organizations. Most of the members were not really
interested in learning, even when they lead a research activity.
They did not formulate research questions, only research

## Slide 389
Case Study – 2...
answers. It could be that the mix of contractors and clients put
everyone in a marketing mode. Marketing always starts with
an answer; research with a question. They hired "researchers"
not to find out or understand reality, but to confirm their own
beliefs.